## R26A Prod 04-07-2021
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-04-07
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Complete | Deployment Lead | Steve Joslin |  | 2022-03-31
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | NA | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-03-31
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : CRQ000021306648 |  | In Progress | Environment Lead | Ginger Altherr |  | 2022-03-31
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod WO0000003101151 – DB Backup - Prod - DB Backup WO0000003094694 – Mock1 - DB Backup - WO0000003094898 DBA Mock 2 - DB Backup - WO0000003098280 DBA Mock 3 - DB Backup - WO0000003116444 DBA Mock QA | Start of outage backup, pre-data backup | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | NA | Environment Lead | Ginger Altherr |  | 2022-03-31
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-31
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-31
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-31
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | In Progress | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-03-31
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Complete | Build Manager | Naresh Methuku |  | 2022-03-31
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Complete | Lead Developer | Chase Farley |  | 2022-03-31
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Complete | Build Manager | Naresh Methuku |  | 2022-03-31
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Go-Live/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Build Manager | Naresh Methuku |  | 2022-03-31
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-31
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment | Sent out on 04/01/2022 | R26 Communications | NA | Change Management | Steve Joslin |  | 2022-03-31
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | In Progress | App / Business Support | Steve Joslin |  | 2022-03-31
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R26 Communications | In Progress | Deployment Lead | Steve Joslin |  | 2022-03-31
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | Complete | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-03-31
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (6 total templates) | 1_Cyber Asset.Last Completion Date_R26 2_Electronic Security.Last NDR Completion_R26 3_Physical Security.Last WDR Completion Date_R26 4_Team.VAR_R26 5_Team.Record Associations_R26 6_Physical Security.Active Status_R26 |  | Not Started | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-04-07
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-04-07
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | Not Started | Change Management | Steve Joslin |  | 2022-04-07 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | Not Started | Application Support | Shawn Linnen |  | 2022-04-07
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | Not Started | Application Support | Shawn Linnen |  | 2022-04-07
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | Not Started | Application Support | Steve Joslin |  | 2022-04-07
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-07
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-07
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Not Started | Deployment Lead | Steve Joslin | 5 | 2022-04-07 | 17:30 |  |  | Chase, Steve, Ginger, Shawn, Derek, Erin , Brandon
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - CALM Training - https://calmtraining.duke-energy.com/RSAarcher/ Mock 2 - PFT1 Mock 3 - QA1 Environment Mock 4 - QA1 Environment Go-live: PROD | Not Started | Deployment Lead | Steve Joslin | 5 | 2022-04-07 | 17:35
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | Not Started | Deployment Lead | Derek Freeze | 5 | 2022-04-07
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-04-07
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | Not Started | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-04-07
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-07 | 18:00
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-04-07 | 18:00
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | Not Started | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-04-07
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 3 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-04-07 | 18:02
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | Not Started | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-04-07
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-04-07 | 18:10
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Not Started | Environment Lead | Ginger Altherr, Peg Parrott | 20 | 2022-04-07
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | NA | Environment Lead | Ginger Altherr |  | 2022-04-07
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | NA | Environment Lead | Ginger Altherr |  | 2022-04-07
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-04-07
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-07
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-07
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK:
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-04-07
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | Not Started | Environment Lead | Ginger Altherr | 3 | 2022-04-07
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-04-07 | 18:30
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-07
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-09
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-07
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-07
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-04-07
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Not Started | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-04-07 | 18:42
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Go-Live/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-04-07 | 18:43
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-04-07
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Not Started | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-04-07
#REF! | 4 | Both |  | Select Execute Mappings |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-04-07 | 19:15
#REF! | 5 | Both | Install Package downloaded from SVN folder |  |  | Not Started |  |  |  | 2022-04-07
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-04-07
#REF! | 7 | Both |  | Click "Install Package" |  | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-04-07
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-04-07 | 19:18
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-04-07 | 19:38
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Not Started | Lead Developer | Chase Farley | 5 | 2022-04-07 |  |  |  | Mock 1 TEST2 - 12 Failures 60 Warnings Mock 2 PFT1 - 12 Failures 60 Warnings Mock 3 QA1 - 12 Failures 71 Warnings Mock 4 QA1 - 12 Failures 89 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Not Started | Lead Developer | Chase Farley |  | 2022-04-07
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Not Started | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-04-07
Install pakage 2 - R26_VAR_Dashboard_Mock1.zip
#REF! | 7 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-04-07
#REF! | 8 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-04-07 | 19:45
#REF! | 9 | Both |  | Click "Install Package" |  | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! | 10 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-04-07
#REF! | 11 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 15 | 2022-04-07
#REF! | 12 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! |  |  | Package 2 Install Validations - R26_VAR_Dashboard_Mock1.zip
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-04-07 | 20:00
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Not Started | Lead Developer | Chase Farley | 5 | 2022-04-07 |  |  |  | Mock 2 PFT1 - 0 Failures 0 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Not Started | Lead Developer | Chase Farley |  | 2022-04-07
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Not Started | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-04-07
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-07
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | Not Started | Application Support | Shawn Linnen |  | 2022-04-07
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | NA | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-04-07
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | NA | Application Support | Chase Farley |  | 2022-04-07 |  |  |  | There were no issues. We shouldn't need to do this step in future mocks.
#REF! | 11 | Both | Smoke Test Functionality
|  |  | RRE CALM Governance Dashboard RRE Patch Management Dashboard RRE Dashboard Vulnerability Assessment (New) Vulnerability Response Review Evidence (New) Wireless Discovery Assessment (New) Network Discovery Assessment (New) Vulnerability Assessment Reporting Workspace (New) | With the New items, we will only confirm existence. |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 10 |  | 20:07
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Technology Profiles Patch Mitigation Plan Vulnerability Assessment Patch Source Evaluations | Not Started | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-04-07 | 20:17 |  |  |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - BES Assets Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Physical Security record with Subform values | Not Started | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-04-07 |  |  |  |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract |  | NA | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R26 - Component List and Manual Configurations | Not Started | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-04-07 | 20:28 |  |  |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Not Started | Lead Developer | Chase Farley |  | 2022-04-07
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | Not Started | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-04-07 | 21:13
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) Step no longer needed | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-04-07
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search Step no longer needed | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-04-07
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values Step no longer needed | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | NA | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-04-07 |  |  |  | This is no longer needed.
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-04-07
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Not Started | Environment Lead | DBA Assigned to Workorder | 30 | 2022-04-07 | 21:15
3 |  | CALM System Outage - Data Import Activities
#REF! |  | Both | 6_Physical Security.Active Status_R26
#REF! | 1 | Both | Upload import template: "6_Physical Security.Active Status_R26" a. Upload – Update Existing Records i. Tracking ID, Business Area, Access Point (Door) Number, Access Point Description, Access Logging and Monitoring Control Measures, Card Reader or Monitor Point Number, Access Point Status | Steps: 1.Save template locally 2. Navigate to Physical Security Application 3. Navigate to Data Import 4. Import file "6_Physical Security.Active Status_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 21:45
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security Application with the following fields: - Tracking ID - Business Area - Access Point (Door) Number - Access Point Description - Access Logging and Monitoring Control Measures - Card Reader or Monitor Point Number - Access Point Status Filter criteria: - Access Logging and Monitoring Control Measures <> No Selection 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 15:40 |  |  | The data changed and so the template required an update and reload.
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Not Started | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 22:00
4.17 |  |  | BSG Configurations
4.17 | 1 | Both | Shruthi's Changes | https://coaction.duke-energy.com/sites/BESCSI_ECT/Tools1/BSG/March BSG Config Changes |  | Not Started | System Administrator | Shruthi | 55 | 2021-04-09 | 22:03
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Not Started | Environment Lead | DBA Assigned to Workorder | 20 | 2022-04-08 | 23:00
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Not Started | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-04-08 | 8:30
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Not Started | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-04-08
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-04-08
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-04-08
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-04-08 | 9:00
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-04-08
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-08
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-09
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-08
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-08
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-04-08
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | NA | Environment Lead | Ginger Altherr | 5 | 2022-04-08 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | NA | Application Support | Shawn Linnen | 1 | 2022-04-08
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-04-08 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-04-08 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-04-08
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-04-08
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-04-08
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-04-08 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | Not Started | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-04-08 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | Not Started | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-04-08
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | Not Started | Environment Lead | Ginger Altherr | 5 | 2022-04-08
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-04-08
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-08
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-09 | 9:00
|  |  | Confirm new scorecard format loaded during data feed |  |  | Not Started |  | Derek Freeze / Chase Farley / Shawn Linnen
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-09
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-04-09 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-04-09
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-09
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-04-09
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-09
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-09
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-09
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-09
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-04-09
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-04-09 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-09
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-04-09 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-04-09 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-04-09
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-04-09
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-04-09
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-04-09
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-04-09
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-04-09 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-10 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-10
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-11 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-11
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-12 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-12
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-13 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-13
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-14 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-14
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-15 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-15

## R26A QA Mock 03-31-2022
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-03-31
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Complete | Deployment Lead | Steve Joslin |  | 2022-03-24
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | NA | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-03-24
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : CRQ000021306648 |  | In Progress | Environment Lead | Ginger Altherr |  | 2022-03-24
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod WO0000003101151 – DB Backup - Prod - DB Backup WO0000003094694 – Mock1 - DB Backup - WO0000003094898 DBA Mock 2 - DB Backup - WO0000003098280 DBA Mock 3 - DB Backup - WO0000003116444 DBA Mock QA | Start of outage backup, pre-data backup | Complete | Environment Lead | Ginger Altherr |  | 2022-03-24
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | NA | Environment Lead | Ginger Altherr |  | 2022-03-24
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-24
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-24
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-24
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | NA | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-03-24
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Complete | Build Manager | Naresh Methuku |  | 2022-03-24
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Complete | Lead Developer | Chase Farley |  | 2022-03-24
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Complete | Build Manager | Naresh Methuku |  | 2022-03-24
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock3/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Build Manager | Naresh Methuku |  | 2022-03-24
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-24
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment |  | R26 Communications | NA | Change Management | Steve Joslin |  | 2022-03-24
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | NA | App / Business Support | Steve Joslin |  | 2022-03-24
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R26 Communications | NA | Deployment Lead | Steve Joslin |  | 2022-03-24
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | NA | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-03-24
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (6 total templates) | 1_Cyber Asset.Last Completion Date_R26 2_Electronic Security.Last NDR Completion_R26 3_Physical Security.Last WDR Completion Date_R26 4_Team.VAR_R26 5_Team.Record Associations_R26 6_Physical Security.Active Status_R26 |  | Complete | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-03-31
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-03-31
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | NA | Change Management | Steve Joslin |  | 2022-03-31 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | NA | Application Support | Shawn Linnen |  | 2022-03-31
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | NA | Application Support | Shawn Linnen |  | 2022-03-31
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | NA | Application Support | Steve Joslin |  | 2022-03-31
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Complete | Deployment Lead | Steve Joslin | 5 | 2022-03-31 | 8:30 |  |  | Chase, Steve, Ginger, Shawn, Derek, Erin , Brandon
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - CALM Training - https://calmtraining.duke-energy.com/RSAarcher/ Mock 2 - PFT1 Mock 3 - QA1 Environment Mock 4 - QA1 Environment Go-live: PROD | Complete | Deployment Lead | Steve Joslin | 5 | 2022-03-31 | 8:35
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | NA | Deployment Lead | Derek Freeze | 5 | 2022-03-31
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-31
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-03-31
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-31
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-31
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | NA | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-31
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 3 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Complete | Application Support | Shawn Linnen | 2 | 2022-03-31 | 8:45 | 8:37 | 8:39
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-03-31
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr | 1 | 2022-03-31 | 8:47
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Complete | Environment Lead | Ginger Altherr, Peg Parrott | 20 | 2022-03-31 |  | 8:39 | 8:53
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-31
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-31
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK:
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-03-31
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | NA | Environment Lead | Ginger Altherr | 3 | 2022-03-31
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-31 | 9:07 | 8:53 | 9:01
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Complete | Environment Lead | Ginger Altherr |  | 2022-03-31
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Complete | Environment Lead | Ginger Altherr |  | 2022-04-02
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-31 |  | 9:01 | 9:03
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-31
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-03-31
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Complete | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-31 | 9:17
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock3/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-31 | 9:17 | 9:03 | 9:06
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-31
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Complete | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-03-31 |  | 10:00 | 10:36
#REF! | 4 | Both |  | Select Execute Mappings |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-31 | 9:47
#REF! | 5 | Both | Install Package downloaded from SVN folder |  |  | Complete |  |  |  | 2022-03-31
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-31
#REF! | 7 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-31 |  | 10:37 | 10:46
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-31 | 9:50 | 10:46 | 11:06
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-31 | 10:10
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-03-31 |  | 11:08 | 11:21 | Mock 1 TEST2 - 12 Failures 60 Warnings Mock 2 PFT1 - 12 Failures 60 Warnings Mock 3 QA1 - 12 Failures 71 Warnings Mock 4 QA1 - 12 Failures 89 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-03-31
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Complete | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-31
Install pakage 2 - R26_VAR_Dashboard_Mock1.zip
#REF! | 7 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-31
#REF! | 8 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-31 | 10:20 | 11:22 | 11:23
#REF! | 9 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! | 10 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-31
#REF! | 11 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 15 | 2022-03-31 |  | 11:23 | 11:31
#REF! | 12 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! |  |  | Package 2 Install Validations - R26_VAR_Dashboard_Mock1.zip
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-31 | 10:30
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-03-31 |  |  |  | Mock 2 PFT1 - 0 Failures 0 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-03-31
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Complete | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-31
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Complete | Application Support | Shawn Linnen | 1 | 2022-03-31 |  | 11:32 | 11:33
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | NA | Application Support | Shawn Linnen |  | 2022-03-31
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | NA | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-31
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | NA | Application Support | Chase Farley |  | 2022-03-31 |  |  |  | There were no issues. We shouldn't need to do this step in future mocks.
#REF! | 11 | Both | Smoke Test Functionality
|  |  | RRE CALM Governance Dashboard RRE Patch Management Dashboard RRE Dashboard Vulnerability Assessment (New) Vulnerability Response Review Evidence (New) Wireless Discovery Assessment (New) Network Discovery Assessment (New) Vulnerability Assessment Reporting Workspace (New) | With the New items, we will only confirm existence. |  | Complete | Application Support | Shawn Linnen / Chase Farley | 10 |  | 10:35 | 11:33 | 11:40
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Technology Profiles Patch Mitigation Plan Vulnerability Assessment Patch Source Evaluations | Complete | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-03-31 | 10:45 | 11:40 | 11:46 |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - BES Assets Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Physical Security record with Subform values | Complete | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-03-31 |  | 11:46 | 11:51 |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract |  | NA | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R26 - Component List and Manual Configurations | Complete | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-03-31 | 11:00 | 11:51 | 12:35 |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Complete | Lead Developer | Chase Farley |  | 2022-03-31
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | NA | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-03-31
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) Step no longer needed | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-03-31
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search Step no longer needed | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-31
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values Step no longer needed | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | NA | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-03-31 |  |  |  | This is no longer needed.
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-03-31
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Complete | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-31 | 11:45 | 12:37 | 12:53
3 |  | CALM System Outage - Data Import Activities
#REF! |  | Both | 6_Physical Security.Active Status_R26
#REF! | 1 | Both | Upload import template: "6_Physical Security.Active Status_R26" a. Upload – Update Existing Records i. Tracking ID, Business Area, Access Point (Door) Number, Access Point Description, Access Logging and Monitoring Control Measures, Card Reader or Monitor Point Number, Access Point Status | Steps: 1.Save template locally 2. Navigate to Physical Security Application 3. Navigate to Data Import 4. Import file "6_Physical Security.Active Status_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 15:30 | 13:35 | 13:41
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security Application with the following fields: - Tracking ID - Business Area - Access Point (Door) Number - Access Point Description - Access Logging and Monitoring Control Measures - Card Reader or Monitor Point Number - Access Point Status Filter criteria: - Access Logging and Monitoring Control Measures <> No Selection 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 15:40 | 13:41 | 14:18 | The data changed and so the template required an update and reload.
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Complete | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 15:45 | 14:18 | 14:20
4.17 |  |  | BSG Configurations
4.17 | 1 | Both | Shruthi's Changes | https://coaction.duke-energy.com/sites/BESCSI_ECT/Tools1/BSG/March BSG Config Changes |  | Complete | System Administrator | Shruthi | 45 | 2021-04-09 | 15:45 | 14:22 | 15:15
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Complete | Environment Lead | DBA Assigned to Workorder | 20 | 2022-04-01 | 15:50 | 15:16 | 15:53
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Complete | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-04-01 | 16:10
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Not Started | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-04-01 | 16:40
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-04-01
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-04-01
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-04-01 | 16:45
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-04-01
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-01
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-02
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-01
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-01 | 16:55
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-04-01
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | NA | Environment Lead | Ginger Altherr | 5 | 2022-04-01 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | NA | Application Support | Shawn Linnen | 1 | 2022-04-01
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-04-01 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-04-01 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-04-01
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-04-01
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-04-01
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-04-01 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | Not Started | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-04-01 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | Not Started | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-04-01
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | Not Started | Environment Lead | Ginger Altherr | 5 | 2022-04-01
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-04-01
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-01
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-02 | 9:00
|  |  | Confirm new scorecard format loaded during data feed |  |  | Not Started |  | Derek Freeze / Chase Farley / Shawn Linnen
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-02
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-04-02 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-04-02
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-02
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-04-02
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-02
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-04-02
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-02
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-02
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-04-02
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-04-02 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-04-02
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-04-02 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-04-02 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-04-02
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-04-02
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-04-02
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-04-02
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-04-02
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-04-02 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-03 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-03
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-04 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-04
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-05 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-05
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-06 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-06
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-07 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-07
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-04-08 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-04-08

## Delayed R26 Prod-03-17-2022
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-03-17
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Complete | Deployment Lead | Steve Joslin |  | 2022-03-10
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | NA | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-03-10
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : CRQ000021306648 |  | In Progress | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod WO0000003101151 – DB Backup - Prod - DB Backup WO0000003094694 – Mock1 - DB Backup - WO0000003094898 DBA Mock 2 - DB Backup - WO0000003098280 DBA Mock 3 | Start of outage backup, pre-data backup | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | NA | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | NA | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-03-10
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Complete | Build Manager | Naresh Methuku |  | 2022-03-10
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Complete | Lead Developer | Chase Farley |  | 2022-03-10
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Complete | Build Manager | Naresh Methuku |  | 2022-03-10
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Go-Live/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Build Manager | Naresh Methuku |  | 2022-03-10
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment | Sent Wednesday 03/09 | R26 Communications | Complete | Change Management | Steve Joslin |  | 2022-03-10
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | In Progress | App / Business Support | Steve Joslin |  | 2022-03-10
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R26 Communications | In Progress | Deployment Lead | Steve Joslin |  | 2022-03-10
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | Complete | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-03-10
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (6 total templates) | 1_Cyber Asset.Last Completion Date_R26 2_Electronic Security.Last NDR Completion_R26 3_Physical Security.Last WDR Completion Date_R26 4_Team.VAR_R26 5_Team.Record Associations_R26 6_Physical Security.Active Status_R26 |  | In Progress | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-03-17
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-03-17
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | Not Started | Change Management | Steve Joslin |  | 2022-03-17 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | Not Started | Application Support | Shawn Linnen |  | 2022-03-17
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | Not Started | Application Support | Shawn Linnen |  | 2022-03-17
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | Not Started | Application Support | Steve Joslin |  | 2022-03-17
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Not Started | Deployment Lead | Steve Joslin | 5 | 2022-03-17 | 8:30 |  |  | Chase, Steve, Ginger, Shawn, Derek, Erin , Brandon, Nitisha
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - CALM Training - https://calmtraining.duke-energy.com/RSAarcher/ Mock 2 - PFT1 Mock 3 - QA1 Environment Go-live: PROD | Not Started | Deployment Lead | Steve Joslin | 5 | 2022-03-17 | 8:35 |  | 8:38
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | Not Started | Deployment Lead | Derek Freeze | 5 | 2022-03-17
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-03-17
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | Not Started | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-03-17
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-03-17
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | Not Started | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-17
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 3 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-03-17 | 8:45 | 8:38 | 8:39
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | Not Started | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-03-17
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-03-17 | 8:47
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Not Started | Environment Lead | Ginger Altherr, Peg Parrott | 20 | 2022-03-17 |  | 8:40 | 8:55
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-17
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-17
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-17
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17 |  | 8:54 | 8:54
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK: | CALM R25 - All Documents (duke-energy.com)
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-03-17
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | Not Started | Environment Lead | Ginger Altherr | 3 | 2022-03-17
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-17 | 9:07 | 8:55 | 9:08
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17 |  | 9:08 | 9:10
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-03-17
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Not Started | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-17 | 9:17
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Go-Live/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17 | 9:17 | 9:10 | 9:14
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Not Started | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-17 |  | 9:14 | 9:27
#REF! | 4 | Both |  | Select Execute Mappings |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17 | 9:47 | 9:27 | 9:31
#REF! | 5 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-17
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 7 | Both |  | Click "Install Package" |  | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-17
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-03-17 | 9:50 | 9:31 | 10:00
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-17 | 10:10 | 10:01 | 10:08
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Not Started | Lead Developer | Chase Farley | 5 | 2022-03-17 |  |  |  | Mock 1 TEST2 - 12 Failures 60 Warnings Mock 2 PFT1 - 12 Failures 60 Warnings Mock 3 PFT1 - 12 Failures 71 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Not Started | Lead Developer | Chase Farley |  | 2022-03-17
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Not Started | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-17
Install pakage 2 - R26_VAR_Dashboard_Mock1.zip
#REF! | 7 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-17
#REF! | 8 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17 | 10:20 | 10:08 | 10:27
#REF! | 9 | Both |  | Click "Install Package" |  | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 10 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-17
#REF! | 11 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-17
#REF! | 12 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! |  |  | Package 2 Install Validations - R26_VAR_Dashboard_Mock1.zip
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-17 | 10:30
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Not Started | Lead Developer | Chase Farley | 5 | 2022-03-17 |  |  |  | Mock 2 PFT1 - 0 Failures 0 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Not Started | Lead Developer | Chase Farley |  | 2022-03-17
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Not Started | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-17
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | Not Started | Application Support | Shawn Linnen |  | 2022-03-17
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | NA | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | NA | Application Support | Chase Farley |  | 2022-03-17 |  |  |  | There were no issues. We shouldn't need to do this step in future mocks.
#REF! | 11 | Both | Smoke Test Functionality
|  |  | RRE CALM Governance Dashboard RRE Patch Management Dashboard RRE Dashboard Vulnerability Assessment (New) Vulnerability Response Review Evidence (New) Wireless Discovery Assessment (New) Network Discovery Assessment (New) Vulnerability Assessment Reporting Workspace (New) | With the New items, we will only confirm existence. |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 10 |  | 10:35 | 10:16 | 10:23
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Technology Profiles Patch Mitigation Plan Vulnerability Assessment Patch Source Evaluations | Not Started | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-03-17 | 10:45 | 10:31 | 10:37 |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - BES Assets Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Physical Security record with Subform values | Not Started | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-03-17 |  | 10:37 | 10:39 |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract |  | NA | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R26 - Component List and Manual Configurations | Not Started | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-03-17 | 11:00 | 10:39 | 12:33 |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Not Started | Lead Developer | Chase Farley |  | 2022-03-17
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | Not Started | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-03-17
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-03-17
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | NA | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-03-17 |  |  |  | This is no longer needed.
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-03-17
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Not Started | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-17 | 11:45 | 12:35 | 13:56
3 |  | CALM System Outage - Data Import Activities
3.1 |  | Both | 1_Cyber Asset.Last Completion Date_R26
|  |  | In Cyber Asset application, inactivate the following calculated fields: - Last Completed Active VAR Date - Next VAR Due Date - Last Completed VAR Date - Days Since Last Active VAR |  |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-18 |  | 15:41 | 15:44
3.1 | #REF! | Both | Upload import template: "1_Cyber Asset.Last Completion Date_R26" a. Upload – Update Existing Records i. Tracking ID, Associated Business Area, Legacy Active VAR Completion Date, Legacy VAR Completion Date | Steps: 1.Save template locally 2. Navigate to Cyber Asset application 3. Navigate to Data Import 4. Import file “1_Cyber Asset.Last Completion Date_R26” 5. Update Existing Records (Tracking ID) 6. Validate import field mapping (everything should automap 1:1 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 60 | 2022-03-18 | 12:15 | 15:44 | 16:12 | First import failed after 70 minutes. Believe its due to the number of Calc jobs being kicked off. Added step to inactivate calc fields prior to import.
3.1 | #REF! | Both | Technical checkout of import template | 1. Build and export report from Cyber Asset with the following fields: Fields: Cyber Asset - Tracking ID - Associated Business Area - Legacy Active VAR Completion Date - Legacy VAR Completion Date Filter: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comment |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-18 | 13:15 | 16:13 | 16:19
#REF! |  | Both | 2_Electronic Security.Last NDR Completion_R26
#REF! | 1 | Both | Upload import template: "2_Electronic Security.Last NDR Completion_R26" a. Upload - Update Existing Records i. Tracking ID, Business Area, Legacy NDR Completion Date | Steps: 1.Save template locally 2. Navigate to Electronic Security application 3. Navigate to Data Import 4. Import file 2_Electronic Security. Last NDR Completion_R26" 5. Create Update Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2022-03-18 | 13:20 | 16:19 | 16:22
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Network Discovery Assessment with the following fields: - Tracking ID - Business Area - Legacy NDR Completion Date Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-18 | 13:35 | 16:22 | 16:24
#REF! |  | Both | 3_Physical Security.Last WDR Completion Date_R26
#REF! | 1 | Both | Upload import template: "3_Physical Security.Last WDR Completion Date_R26" 3_Physical Security.Last WDR Completion Date_R26 b. Upload - Update Existing Records i. Tracking ID; Business Area; Legacy Completion Date | Steps: 1.Save template locally 2. Navigate to Physical Security application 3. Navigate to Data Import 4. Import file "3_Physical Security.Last WDR Completion Date_R26 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 13:40 | 16:24 | 16:27
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security with the following fields: - Tracking ID - Business Area - Legacy WDR Completion Date Use the following filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 13:50 | 16:27 | 16:30
#REF! |  | Both | 4_Team.VAR_R26
#REF! | 1 | Both | Upload import template: "4_Team.VAR_R26" a. Upload – Create New Records i. Team Name, Business Area, Team Lead, Team Reviewer, Team Members | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "4_Team.VAR_R26" 5. Create New Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 13:55 | 16:30 | 16:33
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Team Lead - Team Members - Team Reviewer Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 14:05 | 16:33 | 16:37
#REF! |  | Both | Activate and RUN new data feeds
|  |  | In Cyber Asset application, Reactivate the following calculated fields: - Last Completed Active VAR Date - Next VAR Due Date - Last Completed VAR Date - Days Since Last Active VAR |  |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-18 |  | 16:44 | 16:46
|  |  | Kick off Recalc |  |  | Not Started | [5 empty] | 16:46
|  |  | Run report to confirm Recalc completion | Fields: - Cyber Asset Identifier (Common Name) - Status - Last Completed Active VAR Date - Last Completed VAR Date - Next VAR Due Date - Days Since Last Active VAR Filters: - Impact Rating CONTAINS High, Medium - Status CONTAINS Commissioned - Days Since Last Active VAR = No Value |  | Not Started | [5 empty] | 8:40 | 8:44
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create Network Discovery |  | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Chase Farley | 60 | 2021-10-26 | 14:10 | 11:09 | 11:11
|  |  | Pull an export from Network Discovery Assessment application | 1. Build and export report from Network Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Due Date - Associated Electronic Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 11:11 | 11:13 | With the first export, the due date field was blank. It looks like the recalc on the field is throwing an error. Chase is researching. - Identified issue with ?? Number related to the QA environment. Required an update to manual configs, and a reexecution of that step.
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create VAR |  | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Chase Farley | 60 | 2021-10-26 | 14:10 | 11:18 | 13:15
|  |  | Pull an export from Vulnerability Assessment application | 1. Build and export report from Vulnerability Assessment Application with the following fields: - Tracking ID - Business Area - Due Date - Associated Cyber Asset Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 14:35 | 14:37
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create Wireless Review |  | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Chase Farley | 60 | 2021-10-26 | 14:10 | 11:13 | 11:16
|  |  | Pull an export from Wireless Discovery Assessment application | 1. Build and export report from Wireless Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Due Date - Associated Physical Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 11:16 | 11:18
#REF! |  | Both | 5_Team.Record Associations_R26
|  |  | Erin Makes Template 5 | Erin Makes Template 5 |  | NA | Erin
#REF! | 1 | Both | Upload import template: "5_Team.Record Associations_R26" a. Upload – Update Existing Records i. Team Name, Business Area, Network Discovery Assessment, Wireless Discovery Assessment, Vulnerability Assessment | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "5_Team.Record Associations_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Network Discovery Assessment - Wireless Discovery Assessment - Vulnerability Assessment Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26
#REF! |  | Both | 6_Physical Security.Active Status_R26
#REF! | 1 | Both | Upload import template: "6_Physical Security.Active Status_R26" a. Upload – Update Existing Records i. Tracking ID, Business Area, Access Point (Door) Number, Access Point Description, Access Logging and Monitoring Control Measures, Card Reader or Monitor Point Number, Access Point Status | Steps: 1.Save template locally 2. Navigate to Physical Security Application 3. Navigate to Data Import 4. Import file "6_Physical Security.Active Status_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 15:30 | 16:37 | 16:42
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security Application with the following fields: - Tracking ID - Business Area - Access Point (Door) Number - Access Point Description - Access Logging and Monitoring Control Measures - Card Reader or Monitor Point Number - Access Point Status Filter criteria: - Access Logging and Monitoring Control Measures <> No Selection 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 15:40 | 16:42 | 16:47
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Not Started | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 15:45 | 11:25 | 11:27
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Not Started | Environment Lead | DBA Assigned to Workorder | 20 | 2022-03-18 | 15:50 | 14:55
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Not Started | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-03-18 | 16:10
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Not Started | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-18 | 16:40
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-18
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-18
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-03-18 | 16:45
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-18
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-18
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-18
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-18 | 16:55
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-03-18
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | Not Started | Environment Lead | Ginger Altherr | 5 | 2022-03-18 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-18
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-18 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-03-18 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-03-18
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-03-18
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-03-18
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-18 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | Not Started | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-03-18 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | Not Started | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-03-18
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | Not Started | Environment Lead | Ginger Altherr | 5 | 2022-03-18
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-03-18
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-18
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-19 | 9:00
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-19
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-03-19 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-19
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-19
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-03-19
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-19 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-03-19 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-03-19 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-03-19
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-03-19
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-03-19
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-19
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-03-19
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-03-19 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-20 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-20
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-21 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-21
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-22 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-22
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-23 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-23
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-24 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-24
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-25 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-25

## R26 Mock 3 - 03-10-2022
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-03-10
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Complete | Deployment Lead | Steve Joslin |  | 2022-03-03
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | NA | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-03-03
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : CRQ000021306648 |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-03
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod ?? – DB Backup - Prod - DB Backup WO0000003094694 – Mock1 - DB Backup - WO0000003094898 DBA Mock 2 - DB Backup - WO0000003098280 DBA Mock 3 | Start of outage backup, pre-data backup | Complete | Environment Lead | Ginger Altherr |  | 2022-03-03
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | NA | Environment Lead | Ginger Altherr |  | 2022-03-03
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-03
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-03
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-03
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | NA | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-03-03
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Complete | Build Manager | Naresh Methuku |  | 2022-03-03
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Complete | Lead Developer | Chase Farley |  | 2022-03-03
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Complete | Build Manager | Naresh Methuku |  | 2022-03-03
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock3/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Build Manager | Naresh Methuku |  | 2022-03-03
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-03
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment |  | R25 Communications - All Documents (duke-energy.com) | NA | Change Management | Steve Joslin |  | 2022-03-03
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | NA | App / Business Support | Steve Joslin |  | 2022-03-03
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R25 Communications - All Documents (duke-energy.com) | NA | Deployment Lead | Steve Joslin |  | 2022-03-03
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | NA | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-03-03
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (6 total templates) | 1_Cyber Asset.Last Completion Date_R26 2_Electronic Security.Last NDR Completion_R26 3_Physical Security.Last WDR Completion Date_R26 4_Team.VAR_R26 5_Team.Record Associations_R26 6_Physical Security.Active Status_R26 |  | Complete | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-03-10
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | NA | Change Management | Steve Joslin |  | 2022-03-10 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | NA | Application Support | Shawn Linnen |  | 2022-03-10
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | NA | Application Support | Shawn Linnen |  | 2022-03-10
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | NA | Application Support | Steve Joslin |  | 2022-03-10
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Complete | Deployment Lead | Steve Joslin | 5 | 2022-03-10 | 8:30 |  |  | Chase, Steve, Ginger, Shawn, Derek, Erin , Brandon, Nitisha
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - CALM Training - https://calmtraining.duke-energy.com/RSAarcher/ Mock 2 - PFT1 Mock 3 - QA1 Environment Go-live: PROD | Complete | Deployment Lead | Steve Joslin | 5 | 2022-03-10 | 8:35 |  | 8:38
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | NA | Deployment Lead | Derek Freeze | 5 | 2022-03-10
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-10
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-03-10
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-10
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-10
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | NA | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-10
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 3 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Complete | Application Support | Shawn Linnen | 2 | 2022-03-10 | 8:45 | 8:38 | 8:39
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-03-10
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr | 1 | 2022-03-10 | 8:47
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Complete | Environment Lead | Ginger Altherr, Peg Parrott | 20 | 2022-03-10 |  | 8:40 | 8:55
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-10
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-10 |  | 8:54 | 8:54
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK: | CALM R25 - All Documents (duke-energy.com)
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-03-10
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | NA | Environment Lead | Ginger Altherr | 3 | 2022-03-10
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-10 | 9:07 | 8:55 | 9:08
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Complete | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-12
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-10 |  | 9:08 | 9:10
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-10
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-03-10
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Complete | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-10 | 9:17
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock3/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-10 | 9:17 | 9:10 | 9:14
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-10
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Complete | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-10 |  | 9:14 | 9:27
#REF! | 4 | Both |  | Select Execute Mappings |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-10 | 9:47 | 9:27 | 9:31
#REF! | 5 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-10
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-10
#REF! | 7 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-10
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-03-10 | 9:50 | 9:31 | 10:00
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-10 | 10:10 | 10:01 | 10:08
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-03-10 |  |  |  | Mock 1 TEST2 - 12 Failures 60 Warnings Mock 2 PFT1 - 12 Failures 60 Warnings Mock 3 PFT1 - 12 Failures 71 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-03-10
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Complete | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-10
Install pakage 2 - R26_VAR_Dashboard_Mock1.zip
#REF! | 7 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-10
#REF! | 8 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-10 | 10:20 | 10:08 | 10:27
#REF! | 9 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! | 10 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-10
#REF! | 11 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-10
#REF! | 12 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! |  |  | Package 2 Install Validations - R26_VAR_Dashboard_Mock1.zip
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-10 | 10:30
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-03-10 |  |  |  | Mock 2 PFT1 - 0 Failures 0 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-03-10
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Complete | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-10
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Complete | Application Support | Shawn Linnen | 1 | 2022-03-10
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | NA | Application Support | Shawn Linnen |  | 2022-03-10
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | NA | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-10
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | NA | Application Support | Chase Farley |  | 2022-03-10 |  |  |  | There were no issues. We shouldn't need to do this step in future mocks.
#REF! | 11 | Both | Smoke Test Functionality
|  |  | RRE CALM Governance Dashboard RRE Patch Management Dashboard RRE Dashboard Vulnerability Assessment (New) Vulnerability Response Review Evidence (New) Wireless Discovery Assessment (New) Network Discovery Assessment (New) Vulnerability Assessment Reporting Workspace (New) | With the New items, we will only confirm existence. |  | Complete | Application Support | Shawn Linnen / Chase Farley | 10 |  | 10:35 | 10:16 | 10:23
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Technology Profiles Patch Mitigation Plan Vulnerability Assessment Patch Source Evaluations | Complete | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-03-10 | 10:45 | 10:31 | 10:37 |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - BES Assets Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Physical Security record with Subform values | Complete | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-03-10 |  | 10:37 | 10:39 |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract |  | NA | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R26 - Component List and Manual Configurations | Complete | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-03-10 | 11:00 | 10:39 | 12:33 |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Complete | Lead Developer | Chase Farley |  | 2022-03-10
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | NA | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-03-10
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-03-10
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-10
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | NA | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-03-10 |  |  |  | This is no longer needed.
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-03-10
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Complete | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-10 | 11:45 | 12:35 | 13:56
3 |  | CALM System Outage - Data Import Activities
3.1 |  | Both | 1_Cyber Asset.Last Completion Date_R26
|  |  | In Cyber Asset application, inactivate the following calculated fields: - Last Completed Active VAR Date - Next VAR Due Date - Last Completed VAR Date - Days Since Last Active VAR |  |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-11 |  | 15:41 | 15:44
3.1 | #REF! | Both | Upload import template: "1_Cyber Asset.Last Completion Date_R26" a. Upload – Update Existing Records i. Tracking ID, Associated Business Area, Legacy Active VAR Completion Date, Legacy VAR Completion Date | Steps: 1.Save template locally 2. Navigate to Cyber Asset application 3. Navigate to Data Import 4. Import file “1_Cyber Asset.Last Completion Date_R26” 5. Update Existing Records (Tracking ID) 6. Validate import field mapping (everything should automap 1:1 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 60 | 2022-03-11 | 12:15 | 15:44 | 16:12 | First import failed after 70 minutes. Believe its due to the number of Calc jobs being kicked off. Added step to inactivate calc fields prior to import.
3.1 | #REF! | Both | Technical checkout of import template | 1. Build and export report from Cyber Asset with the following fields: Fields: Cyber Asset - Tracking ID - Associated Business Area - Legacy Active VAR Completion Date - Legacy VAR Completion Date Filter: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comment |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-11 | 13:15 | 16:13 | 16:19
#REF! |  | Both | 2_Electronic Security.Last NDR Completion_R26
#REF! | 1 | Both | Upload import template: "2_Electronic Security.Last NDR Completion_R26" a. Upload - Update Existing Records i. Tracking ID, Business Area, Legacy NDR Completion Date | Steps: 1.Save template locally 2. Navigate to Electronic Security application 3. Navigate to Data Import 4. Import file 2_Electronic Security. Last NDR Completion_R26" 5. Create Update Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2022-03-11 | 13:20 | 16:19 | 16:22
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Network Discovery Assessment with the following fields: - Tracking ID - Business Area - Legacy NDR Completion Date Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-11 | 13:35 | 16:22 | 16:24
#REF! |  | Both | 3_Physical Security.Last WDR Completion Date_R26
#REF! | 1 | Both | Upload import template: "3_Physical Security.Last WDR Completion Date_R26" 3_Physical Security.Last WDR Completion Date_R26 b. Upload - Update Existing Records i. Tracking ID; Business Area; Legacy Completion Date | Steps: 1.Save template locally 2. Navigate to Physical Security application 3. Navigate to Data Import 4. Import file "3_Physical Security.Last WDR Completion Date_R26 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 13:40 | 16:24 | 16:27
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security with the following fields: - Tracking ID - Business Area - Legacy WDR Completion Date Use the following filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 13:50 | 16:27 | 16:30
#REF! |  | Both | 4_Team.VAR_R26
#REF! | 1 | Both | Upload import template: "4_Team.VAR_R26" a. Upload – Create New Records i. Team Name, Business Area, Team Lead, Team Reviewer, Team Members | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "4_Team.VAR_R26" 5. Create New Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 13:55 | 16:30 | 16:33
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Team Lead - Team Members - Team Reviewer Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 14:05 | 16:33 | 16:37
#REF! |  | Both | Activate and RUN new data feeds
|  |  | In Cyber Asset application, Reactivate the following calculated fields: - Last Completed Active VAR Date - Next VAR Due Date - Last Completed VAR Date - Days Since Last Active VAR |  |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-11 |  | 16:44 | 16:46
|  |  | Kick off Recalc |  |  | Complete | [5 empty] | 16:46
|  |  | Run report to confirm Recalc completion | Fields: - Cyber Asset Identifier (Common Name) - Status - Last Completed Active VAR Date - Last Completed VAR Date - Next VAR Due Date - Days Since Last Active VAR Filters: - Impact Rating CONTAINS High, Medium - Status CONTAINS Commissioned - Days Since Last Active VAR = No Value |  | Complete | [5 empty] | 8:40 | 8:44
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create Network Discovery |  | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Chase Farley | 60 | 2021-10-26 | 14:10 | 11:09 | 11:11
|  |  | Pull an export from Network Discovery Assessment application | 1. Build and export report from Network Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Due Date - Associated Electronic Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 11:11 | 11:13 | With the first export, the due date field was blank. It looks like the recalc on the field is throwing an error. Chase is researching. - Identified issue with ?? Number related to the QA environment. Required an update to manual configs, and a reexecution of that step.
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create VAR |  | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Chase Farley | 60 | 2021-10-26 | 14:10 | 11:18 | 13:15
|  |  | Pull an export from Vulnerability Assessment application | 1. Build and export report from Vulnerability Assessment Application with the following fields: - Tracking ID - Business Area - Due Date - Associated Cyber Asset Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 14:35 | 14:37
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create Wireless Review |  | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Chase Farley | 60 | 2021-10-26 | 14:10 | 11:13 | 11:16
|  |  | Pull an export from Wireless Discovery Assessment application | 1. Build and export report from Wireless Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Due Date - Associated Physical Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 11:16 | 11:18
#REF! |  | Both | 5_Team.Record Associations_R26
|  |  | Erin Makes Template 5 | Erin Makes Template 5 |  | NA | Erin
#REF! | 1 | Both | Upload import template: "5_Team.Record Associations_R26" a. Upload – Update Existing Records i. Team Name, Business Area, Network Discovery Assessment, Wireless Discovery Assessment, Vulnerability Assessment | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "5_Team.Record Associations_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Network Discovery Assessment - Wireless Discovery Assessment - Vulnerability Assessment Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26
#REF! |  | Both | 6_Physical Security.Active Status_R26
#REF! | 1 | Both | Upload import template: "6_Physical Security.Active Status_R26" a. Upload – Update Existing Records i. Tracking ID, Business Area, Access Point (Door) Number, Access Point Description, Access Logging and Monitoring Control Measures, Card Reader or Monitor Point Number, Access Point Status | Steps: 1.Save template locally 2. Navigate to Physical Security Application 3. Navigate to Data Import 4. Import file "6_Physical Security.Active Status_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 15:30 | 16:37 | 16:42
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security Application with the following fields: - Tracking ID - Business Area - Access Point (Door) Number - Access Point Description - Access Logging and Monitoring Control Measures - Card Reader or Monitor Point Number - Access Point Status Filter criteria: - Access Logging and Monitoring Control Measures <> No Selection 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 | 15:40 | 16:42 | 16:47
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Complete | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 15:45 | 11:25 | 11:27
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Complete | Environment Lead | DBA Assigned to Workorder | 20 | 2022-03-11 | 15:50 | 14:55
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Complete | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-03-11 | 16:10
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Complete | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-11 | 16:40
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Complete | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-11
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | NA | Environment Lead | Ginger Altherr | 2 | 2022-03-11
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Complete | Application Support | Shawn Linnen | 2 | 2022-03-11 | 16:45
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-11
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Complete | Environment Lead | Ginger Altherr |  | 2022-03-11
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-12
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-11
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-11 | 16:55
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-03-11
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | NA | Environment Lead | Ginger Altherr | 5 | 2022-03-11 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | NA | Application Support | Shawn Linnen | 1 | 2022-03-11
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-11 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-03-11 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-03-11
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-03-11
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-03-11
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-11 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-03-11 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-03-11
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 5 | 2022-03-11
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | NA | Delivery Lead | Derek Freeze | 1 | 2022-03-11
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support | Shawn Linnen | 1 | 2022-03-11
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-12 | 9:00
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-12
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-03-12 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-12
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-12
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-12
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-12
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-12
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-12
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-12
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-03-12
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-12 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-12
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-03-12 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-03-12 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-03-12
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-03-12
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-03-12
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-12
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-03-12
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-03-12 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-13 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-13
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-14 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-14
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-15 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-15
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-16 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-16
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-17 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-17
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-18 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-18

## R26 Mock 2 - 03-03-2022
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-03-03
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Complete | Deployment Lead | Steve Joslin |  | 2022-02-24
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | NA | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-02-24
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : CRQ000021306648 |  | NA | Environment Lead | Ginger Altherr |  | 2022-02-24
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod ?? – DB Backup - Prod - DB Backup WO0000003094694 – Mock1 - DB Backup - WO0000003094898 DBA Mock 2 - DB Backup - WO0000003098280 DBA Mock 3 | Start of outage backup, pre-data backup | Complete | Environment Lead | Ginger Altherr |  | 2022-02-24
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | NA | Environment Lead | Ginger Altherr |  | 2022-02-24
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-24
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-24
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-24
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | NA | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-02-24
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Complete | Build Manager | Naresh Methuku |  | 2022-02-24
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Complete | Lead Developer | Chase Farley |  | 2022-02-24
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Complete | Build Manager | Naresh Methuku |  | 2022-02-24
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock2/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Build Manager | Naresh Methuku |  | 2022-02-24
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-24
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment |  | R25 Communications - All Documents (duke-energy.com) | NA | Change Management | Steve Joslin |  | 2022-02-24
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | NA | App / Business Support | Steve Joslin |  | 2022-02-24
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R25 Communications - All Documents (duke-energy.com) | NA | Deployment Lead | Steve Joslin |  | 2022-02-24
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | NA | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-02-24
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (6 total templates) | 1_Cyber Asset.Last Completion Date_R26 2_Electronic Security.Last NDR Completion_R26 3_Physical Security.Last WDR Completion Date_R26 4_Team.VAR_R26 5_Team.Record Associations_R26 6_Physical Security.Active Status_R26 |  | Complete | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-03-03
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-03-03
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | NA | Change Management | Steve Joslin |  | 2022-03-03 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | NA | Application Support | Shawn Linnen |  | 2022-03-03
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | NA | Application Support | Shawn Linnen |  | 2022-03-03
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | NA | Application Support | Steve Joslin |  | 2022-03-03
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Complete | Environment Lead | Ginger Altherr |  | 2022-03-03
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr |  | 2022-03-03
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Complete | Deployment Lead | Steve Joslin | 5 | 2022-03-03 | 5:30 |  |  | Chase, Steve, Ginger, Derek, Erin , Brandon, Nitisha
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - CALM Training - https://calmtraining.duke-energy.com/RSAarcher/ Mock 2 - PFT1 Mock 3 - QA1 Environment Go-live: PROD | Complete | Deployment Lead | Steve Joslin | 5 | 2022-03-03 | 17:35
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | NA | Deployment Lead | Derek Freeze | 5 | 2022-03-03 | 17:40
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-03
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-03-03
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-03 | 18:00
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-03 | 18:00
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | NA | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-03
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 3 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Complete | Application Support | Shawn Linnen | 2 | 2022-03-03 |  | 8:46 | 8:48
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-03-03 | 18:05
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr | 1 | 2022-03-03 | 18:13
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Complete | Environment Lead | Ginger Altherr, Peg Parrott | 30 | 2022-03-03 |  | 8:48 | 9:08
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-03
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-03
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-03 |  | 8:49 | 8:53
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-03
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-03
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK: | CALM R25 - All Documents (duke-energy.com)
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-03-03 | 18:43
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | NA | Environment Lead | Ginger Altherr | 3 | 2022-03-03 | 19:00
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Complete | Environment Lead | Ginger Altherr | 10 | 2022-03-03 |  | 9:08 | 9:14
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Complete | Environment Lead | Ginger Altherr |  | 2022-03-03
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Complete | Environment Lead | Ginger Altherr |  | 2022-03-05
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-03 |  | 9:14 | 9:15
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Complete | Application Support | Shawn Linnen | 1 | 2022-03-03
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-03-03
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Complete | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-03 | 19:12
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock2/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 R26_VAR_Dashboard_Mock1.zip | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-03 | 19:12 | 9:16 | 9:19
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-03
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Complete | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-03-03 | 19:14 | 9:19 | 9:50
#REF! | 4 | Both | C | Select Execute Mappings |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-03
#REF! | 5 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-03
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-03
#REF! | 7 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-03
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-03 | 19:38 | 9:50 | 10:10
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-03 | 20:13 | 10:12 | 10:22
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-03-03 |  |  |  | Mock 1 TEST2 - 12 Failures 60 Warnings Mock 2 PFT1 - 12 Failures 60 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-03-03
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Complete | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-03
Install pakage 2 - R26_VAR_Dashboard_Mock1.zip
#REF! | 7 | Both | Install Package downloaded from SVN folder | [6 empty] | 2022-03-03
#REF! | 8 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-03 |  | 10:17 | 10:18
#REF! | 9 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! | 10 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-03
#REF! | 11 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 30 | 2022-03-03 | 19:38 | 10:18 | 10:19
#REF! | 12 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! |  |  | Package 2 Install Validations - R26_VAR_Dashboard_Mock1.zip
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-03 | 20:13
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-03-03 |  |  |  | Mock 1 TEST2 - 0 Failures 0 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-03-03
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Complete | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-03
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Complete | Application Support | Shawn Linnen | 1 | 2022-03-03
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | NA | Application Support | Shawn Linnen |  | 2022-03-03
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | NA | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-03
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | NA | Application Support | Chase Farley |  | 2022-03-03 |  |  |  | There were no issues. We shouldn't need to do this step in future mocks.
#REF! | 11 | Both | Smoke Test Functionality
|  |  | RRE CALM Governance Dashboard RRE Patch Management Dashboard RRE Dashboard Vulnerability Assessment (New) Vulnerability Response Review Evidence (New) Wireless Discovery Assessment (New) Network Discovery Assessment (New) Cyber Vulnerability Assessment (CVA) Workspace (New) | With the New items, we will only confirm existence. |  | Complete | Application Support | Shawn Linnen / Chase Farley | 10 |  |  | 10;20 AM | 10:35
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Technology Profiles Patch Mitigation Plan Vulnerability Assessment Patch Source Evaluations | Complete | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-03-03 | 20:41 | 10:35 | 13:11 |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - BES Assets Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Physical Security record with Subform values | Complete | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-03-03 |  | 13:11 | 13:14 |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract |  | NA | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R26 - Component List and Manual Configurations | Complete | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-03-03 | 20:52 | 13:14 | 13:55 |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Complete | Lead Developer | Chase Farley |  | 2022-03-03
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | NA | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-03-03 | 21:37
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-03-03
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-03
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | NA | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-03-03 | 12:22 |  |  | This is no longer needed.
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-03-03
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Complete | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-03 | 21:45 | 13:56 | 14:26
3 |  | CALM System Outage - Data Import Activities
3.1 |  | Both | 1_Cyber Asset.Last Completion Date_R26
3.1 | #REF! | Both | Upload import template: "1_Cyber Asset.Last Completion Date_R26" a. Upload – Update Existing Records i. Tracking ID, Associated Business Area, Legacy Active VAR Completion Date, Legacy VAR Completion Date | Steps: 1.Save template locally 2. Navigate to Cyber Asset application 3. Navigate to Data Import 4. Import file “1_Cyber Asset.Last Completion Date_R26” 5. Update Existing Records (Tracking ID) 6. Validate import field mapping (everything should automap 1:1 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 60 | 2022-03-04 |  | 14:26 | 15:47
3.1 | #REF! | Both | Technical checkout of import template | 1. Build and export report from Cyber Asset with the following fields: Fields: Cyber Asset - Tracking ID - Associated Business Area - Legacy Active VAR Completion Date - Legacy VAR Completion Date Filter: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comment |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-04 |  | 15:47 | 15:55
#REF! |  | Both | 2_Electronic Security.Last NDR Completion_R26
#REF! | 1 | Both | Upload import template: "2_Electronic Security.Last NDR Completion_R26" a. Upload - Update Existing Records i. Tracking ID, Business Area, Legacy NDR Completion Date | Steps: 1.Save template locally 2. Navigate to Electronic Security application 3. Navigate to Data Import 4. Import file 2_Electronic Security. Last NDR Completion_R26" 5. Create Update Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2022-03-04 | 22:08 | 15:55 | 16:10
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Network Discovery Assessment with the following fields: - Tracking ID - Business Area - Legacy NDR Completion Date Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-04 |  | 16:10 | 16:16
#REF! |  | Both | 3_Physical Security.Last WDR Completion Date_R26
#REF! | 1 | Both | Upload import template: "3_Physical Security.Last WDR Completion Date_R26" 3_Physical Security.Last WDR Completion Date_R26 b. Upload - Update Existing Records i. Tracking ID; Business Area; Legacy Completion Date | Steps: 1.Save template locally 2. Navigate to Physical Security application 3. Navigate to Data Import 4. Import file "3_Physical Security.Last WDR Completion Date_R26 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 22:15 | 16:16 | 16:22
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security with the following fields: - Tracking ID - Business Area - Legacy WDR Completion Date Use the following filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 16:22 | 16:25
#REF! |  | Both | 4_Team.VAR_R26
#REF! | 1 | Both | Upload import template: "4_Team.VAR_R26" a. Upload – Create New Records i. Team Name, Business Area, Team Lead, Team Reviewer, Team Members | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "4_Team.VAR_R26" 5. Create New Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 16:26 | 16:31
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Team Lead - Team Members - Team Reviewer Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 16:31 | 16:33
#REF! |  | Both | 5_Team.Record Associations_R26
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create Wireless Review Vulnerability Assessment - Create Network Discovery Vulnerability Assessment - Create VAR | Activate the following datafeeds: Vulnerability Assessment - Create Wireless Review Vulnerability Assessment - Create Network Discovery Vulnerability Assessment - Create VAR | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2021-10-26
|  |  | Pull an export from Wireless Discovery Assessment application | 1. Build and export report from Wireless Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Associated Physical Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
|  |  | Pull an export from Network Discovery Assessment application | 1. Build and export report from Network Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Associated Electronic Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
|  |  | Pull an export from Vulnerability Assessment application | 1. Build and export report from Vulnerability Assessment Application with the following fields: - Tracking ID - Business Area - Associated Cyber Asset Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
|  |  | Erin Makes Template 5 | Erin Makes Template 5 |  | NA | Erin
#REF! | 1 | Both | Upload import template: "5_Team.Record Associations_R26" a. Upload – Update Existing Records i. Team Name, Business Area, Network Discovery Assessment, Wireless Discovery Assessment, Vulnerability Assessment | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "5_Team.Record Associations_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Network Discovery Assessment - Wireless Discovery Assessment - Vulnerability Assessment Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | NA | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26
#REF! |  | Both | 6_Physical Security.Active Status_R26
#REF! | 1 | Both | Upload import template: "6_Physical Security.Active Status_R26" a. Upload – Update Existing Records i. Tracking ID, Business Area, Access Point (Door) Number, Access Point Description, Access Logging and Monitoring Control Measures, Card Reader or Monitor Point Number, Access Point Status | Steps: 1.Save template locally 2. Navigate to Physical Security Application 3. Navigate to Data Import 4. Import file "6_Physical Security.Active Status_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 16:33 | 16:39
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security Application with the following fields: - Tracking ID - Business Area - Access Point (Door) Number - Access Point Description - Access Logging and Monitoring Control Measures - Card Reader or Monitor Point Number - Access Point Status Filter criteria: - Access Logging and Monitoring Control Measures <> No Selection 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 16:39 | 16:47
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments - PSP: Create CALM Revision History |  | Complete | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 23:05 | 16:48 | 16:52
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Complete | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-04 | 23:08 | 16:52 | 17:10
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Not Started | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-03-04 | 8:30
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Not Started | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-04 | 9:00
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-04
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | NA | Environment Lead | Ginger Altherr | 2 | 2022-03-04
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-03-04 | 9:05
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-04
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-04
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-05
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-04
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-04
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-03-04
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | NA | Environment Lead | Ginger Altherr | 5 | 2022-03-04 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | NA | Application Support | Shawn Linnen | 1 | 2022-03-04
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-04 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-03-04 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-03-04
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-03-04
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-03-04
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-04 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-03-04 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-03-04
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 5 | 2022-03-04
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | NA | Delivery Lead | Derek Freeze | 1 | 2022-03-04
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support | Shawn Linnen | 1 | 2022-03-04
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-05 | 9:00
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-05
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-03-05 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-05
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-05
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-05
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-05
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-05
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-05
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-05
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-03-05
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-05 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-05
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-03-05 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-03-05 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-03-05
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-03-05
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-03-05
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-05
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-03-05
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-03-05 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-06 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-06
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-07 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-07
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-08 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-08
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-09 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-09
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-10 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-10
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-11 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-11

## R26 Mock 1 - 02-24-2022
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-02-24
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Complete | Deployment Lead | Steve Joslin |  | 2022-02-17
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | NA | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-02-17
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : ?? |  | NA | Environment Lead | Ginger Altherr |  | 2022-02-17
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod ?? – DB Backup - Prod - DB Backup WO0000003094694 – Mock1 - DB Backup ?? – Mock2 - DB Backup ?? – Mock3 QA | Start of outage backup, pre-data backup | Complete | Environment Lead | Ginger Altherr |  | 2022-02-17
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | NA | Environment Lead | Ginger Altherr |  | 2022-02-17
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-17
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Complete | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-17
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-17
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | NA | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-02-17
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Complete | Build Manager | Naresh Methuku |  | 2022-02-17
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Complete | Lead Developer | Chase Farley |  | 2022-02-17
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Complete | Build Manager | Naresh Methuku |  | 2022-02-17
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock1/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 | Complete | Build Manager | Naresh Methuku |  | 2022-02-17
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-02-17
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment |  | R25 Communications - All Documents (duke-energy.com) | NA | Change Management | Steve Joslin |  | 2022-02-17
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | NA | App / Business Support | Steve Joslin |  | 2022-02-17
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R25 Communications - All Documents (duke-energy.com) | NA | Deployment Lead | Steve Joslin |  | 2022-02-17
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | NA | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-02-17
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (6 total templates) | 1_Cyber Asset.Last Completion Date_R26 2_Electronic Security.Last NDR Completion_R26 3_Physical Security.Last WDR Completion Date_R26 4_Team.VAR_R26 5_Team.Record Associations_R26 6_Physical Security.Active Status_R26 |  | Complete | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-02-24
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-02-24
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | NA | Change Management | Steve Joslin |  | 2022-02-24 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | NA | Application Support | Shawn Linnen |  | 2022-02-24
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | NA | Application Support | Shawn Linnen |  | 2022-02-24
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | NA | Application Support | Steve Joslin |  | 2022-02-24
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Complete | Environment Lead | Ginger Altherr |  | 2022-02-24
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr |  | 2022-02-24
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Complete | Deployment Lead | Steve Joslin | 5 | 2022-02-24 | 17:30 |  |  | Chase, Steve, Ginger, TaKayla, Derek,Erin , Brandon
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - CALM Training - https://calmtraining.duke-energy.com/RSAarcher/ Mock 2 - PFT1 Mock 3 - QA1 Environment Go-live: PROD | Complete | Deployment Lead | Steve Joslin | 5 | 2022-02-24 | 17:35
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | NA | Deployment Lead | Derek Freeze | 5 | 2022-02-24 | 17:40
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr | 1 | 2022-02-24
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-02-24
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | NA | Environment Lead | Ginger Altherr |  | 2022-02-24 | 18:00
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 1 | 2022-02-24 | 18:00
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | NA | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-02-24
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 2 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments New with R25 (for next time) - PSP: Create CALM Revision History |  | Complete | Application Support | Shawn Linnen | 2 | 2022-02-24 |  | 8:43 | 8:44
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-02-24 | 18:05
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Complete | Environment Lead | Ginger Altherr | 1 | 2022-02-24 | 18:13 | 8:45 | 9:05
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Complete | Environment Lead | Ginger Altherr, Peg Parrott | 30 | 2022-02-24
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | NA | Environment Lead | Ginger Altherr |  | 2022-02-24
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | NA | Environment Lead | Ginger Altherr |  | 2022-02-24
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Complete | Environment Lead | Ginger Altherr | 10 | 2022-02-24 |  | 8:54 | 8:57
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Complete | Environment Lead | Ginger Altherr |  | 2022-02-24
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Complete | Application Support | Shawn Linnen | 1 | 2022-02-24
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK: | CALM R25 - All Documents (duke-energy.com)
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-02-24 | 18:43
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | NA | Environment Lead | Ginger Altherr | 3 | 2022-02-24 | 19:00
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Complete | Environment Lead | Ginger Altherr | 10 | 2022-02-24 |  | 9:05 | 9:10
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Complete | Environment Lead | Ginger Altherr |  | 2022-02-24
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Complete | Environment Lead | Ginger Altherr |  | 2022-02-26 |  | 9:11 | 9:12
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Complete | Application Support | Shawn Linnen | 1 | 2022-02-24
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Complete | Application Support | Shawn Linnen | 1 | 2022-02-24
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-02-24
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Complete | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-02-24 | 19:12
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for R26: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR26/Mock1/ | Package Name: CALMPACKAGE_R26_Components_Sprint_142_DEV1_Feature_Complete_02222022 | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-02-24 | 19:12
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-02-24 |  | 9:13 | 9:15
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Complete | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-02-24 | 19:14 | 10:33 | 15:19
#REF! | 4 | Both |  | Select Execute Mappings |  | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-02-24 |  | 15:19
#REF! | 5 | Both | Install Package downloaded from SVN folder |  |  | Complete |  |  |  | 2022-02-24
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-02-24
#REF! | 7 | Both |  | Click "Install Package" |  | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-02-24
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-02-24
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Complete | Application Support | Shawn Linnen / Chase Farley | 35 | 2022-02-24 | 19:38 | 15:23 | 15:44
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-02-24
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Complete | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-02-24 | 20:13 | 15:44 | 15:52
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-02-24
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Complete | Lead Developer | Chase Farley | 5 | 2022-02-24 |  |  |  | Mock 1 TEST2 - 12 Failures 60 Warnings
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Complete | Application Support | Shawn Linnen / Chase Farley |  | 2022-02-24
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Complete | Lead Developer | Chase Farley |  | 2022-02-24
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | In Progress | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-02-24
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Complete | Application Support | Shawn Linnen | 1 | 2022-02-24 |  | 15:53 | 15:54
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | NA | Application Support | Shawn Linnen |  | 2022-02-24
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | Complete | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-02-24 |  | 15:54 | 15:56
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | Complete | Application Support | Chase Farley |  | 2022-02-24 |  | 15:56 | 16:09 | There were no issues. We shouldn't need to do this step in future mocks.
#REF! | 11 | Both | Smoke Test Functionality
|  |  | RRE CALM Governance Dashboard RRE Patch Management Dashboard Vulnerability Assessment (New) Vulnerability Response Review Evidence (New) Wireless Discovery Assessment (New) Network Discovery Assessment (New) Cyber Vulnerability Assessment (CVA) Workspace (New) | With the New items, we will only confirm existence. |  | Complete | Application Support | Shawn Linnen / Chase Farley |  |  |  | 15:57 | 16:03
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Technology Profiles Patch Mitigation Plan Vulnerability Assessment Patch Source Evaluations | Complete | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-02-24 | 20:41 | 15:57 | 16:09 |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - BES Assets Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Physical Security record with Subform values | Complete | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-02-24 |  | 16:10 | 16:11 |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract |  | NA | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R25 - Component List and Manual Configurations | Complete | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-02-24 | 20:52 | 17:02 | 17:51 |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Complete | Lead Developer | Chase Farley |  | 2022-02-24
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-02-24
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | NA | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-02-24 | 21:37
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | NA | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-02-24
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-02-24
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | Complete | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-02-24 | 12:22 |  |  | This is no longer needed.
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-02-24
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Complete | Environment Lead | DBA Assigned to Workorder | 30 | 2022-02-24 | 21:45
3 |  | CALM System Outage - Data Import Activities
3.1 |  | Both | 1_Cyber Asset.Last Completion Date_R26
3.1 | #REF! | Both | Upload import template: "1_Cyber Asset.Last Completion Date_R26" a. Upload – Update Existing Records i. Tracking ID, Associated Business Area, Legacy Active VAR Completion Date, Legacy VAR Completion Date | Steps: 1.Save template locally 2. Navigate to Cyber Asset application 3. Navigate to Data Import 4. Import file “1_Cyber Asset.Last Completion Date_R26” 5. Update Existing Records (Tracking ID) 6. Validate import field mapping (everything should automap 1:1 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 3 | 2022-02-25 |  | 8:43 | 8:51
3.1 | #REF! | Both | Technical checkout of import template | 1. Build and export report from Cyber Asset with the following fields: Fields: Cyber Asset - Tracking ID - Associated Business Area - Legacy Active VAR Completion Date - Legacy VAR Completion Date Filter: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comment |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-02-25 |  | 8:51 | 9:00
#REF! |  | Both | 2_Electronic Security.Last NDR Completion_R26
#REF! | 1 | Both | Upload import template: "2_Electronic Security.Last NDR Completion_R26" a. Upload - Update Existing Records i. Tracking ID, Business Area, Legacy NDR Completion Date | Steps: 1.Save template locally 2. Navigate to Electronic Security application 3. Navigate to Data Import 4. Import file 2_Electronic Security. Last NDR Completion_R26" 5. Create Update Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2022-02-25 | 22:08 | 9:00 | 9:02
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Network Discovery Assessment with the following fields: - Tracking ID - Business Area - Legacy NDR Completion Date Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-02-25 |  | 9:02 | 9:06
#REF! |  | Both | 3_Physical Security.Last WDR Completion Date_R26
#REF! | 1 | Both | Upload import template: "3_Physical Security.Last WDR Completion Date_R26" 3_Physical Security.Last WDR Completion Date_R26 b. Upload - Update Existing Records i. Tracking ID; Business Area; Legacy Completion Date | Steps: 1.Save template locally 2. Navigate to Physical Security application 3. Navigate to Data Import 4. Import file "3_Physical Security.Last WDR Completion Date_R26 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 22:15 | 9:06 | 9:07
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security with the following fields: - Tracking ID - Business Area - Legacy WDR Completion Date Use the following filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 9:07 | 9:11
#REF! |  | Both | 4_Team.VAR_R26
#REF! | 1 | Both | Upload import template: "4_Team.VAR_R26" a. Upload – Create New Records i. Team Name, Business Area, Team Lead, Team Reviewer, Team Members | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "4_Team.VAR_R26" 5. Create New Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 9:11 | 9:13
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Team Lead - Team Members - Team Reviewer Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 9:13 | 9:17
#REF! |  | Both | 5_Team.Record Associations_R26
|  |  | Activate and RUN the following datafeeds: Vulnerability Assessment - Create Wireless Review Vulnerability Assessment - Create Network Discovery Vulnerability Assessment - Create VAR | Activate the following datafeeds: Vulnerability Assessment - Create Wireless Review Vulnerability Assessment - Create Network Discovery Vulnerability Assessment - Create VAR | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Chase Farley | 10 | 2021-10-26 |  | 9:17 | 10:35
|  |  | Pull an export from Wireless Discovery Assessment application | 1. Build and export report from Wireless Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Associated Physical Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 9:32 | 9:34
|  |  | Pull an export from Network Discovery Assessment application | 1. Build and export report from Network Discovery Assessment Application with the following fields: - Tracking ID - Business Area - Associated Electronic Security Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
|  |  | Pull an export from Vulnerability Assessment application | 1. Build and export report from Vulnerability Assessment Application with the following fields: - Tracking ID - Business Area - Associated Cyber Asset Filter criteria: - None 2. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 10:35 | 10:38
|  |  | Erin Makes Template 5 | Erin Makes Template 5 |  | Complete | Erin |  |  |  |  | 10:38 | 10:39
#REF! | 1 | Both | Upload import template: "5_Team.Record Associations_R26" a. Upload – Update Existing Records i. Team Name, Business Area, Network Discovery Assessment, Wireless Discovery Assessment, Vulnerability Assessment | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "5_Team.Record Associations_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 10:39 | 10:51
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Network Discovery Assessment - Wireless Discovery Assessment - Vulnerability Assessment Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 10:51 | 10:51
#REF! |  | Both | 6_Physical Security.Active Status_R26
#REF! | 1 | Both | Upload import template: "6_Physical Security.Active Status_R26" a. Upload – Update Existing Records i. Tracking ID, Business Area, Access Point (Door) Number, Access Point Description, Access Logging and Monitoring Control Measures, Card Reader or Monitor Point Number, Access Point Status | Steps: 1.Save template locally 2. Navigate to Physical Security Application 3. Navigate to Data Import 4. Import file "6_Physical Security.Active Status_R26" 5. Updating Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import | https://coaction.duke-energy.com/sites/IT_BESCSI_NCTP/SitePages/Home.aspx | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 |  | 9:49 | 9:56
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Physical Security Application with the following fields: - Tracking ID - Business Area - Access Point (Door) Number - Access Point Description - Access Logging and Monitoring Control Measures - Card Reader or Monitor Point Number - Access Point Status Filter criteria: - Access Logging and Monitoring Control Measures <> No Selection 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Complete | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26 |  | 9:56 | 10:02
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Patch Assessment Create - PSP: Create CALM Revision History |  | Complete | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 23:05 | 10:52 | 10:56
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Complete | Environment Lead | DBA Assigned to Workorder | 30 | 2022-02-25 | 23:08 | 11:00 | 11:41
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Not Started | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-02-25 | 8:30
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Not Started | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-02-25 | 9:00
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-02-25
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | NA | Environment Lead | Ginger Altherr | 2 | 2022-02-25
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-02-25 | 9:05
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-02-25
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-02-25
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-02-26
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-02-25
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-02-25
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-02-25
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | NA | Environment Lead | Ginger Altherr | 5 | 2022-02-25 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | NA | Application Support | Shawn Linnen | 1 | 2022-02-25
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-02-25 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-02-25 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-02-25
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-02-25
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-02-25
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-02-25 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-02-25 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-02-25
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 5 | 2022-02-25
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | NA | Delivery Lead | Derek Freeze | 1 | 2022-02-25
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support | Shawn Linnen | 1 | 2022-02-25
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-02-26 | 9:00
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-02-26
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-02-26 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-02-26
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-02-26
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-02-26
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-02-26
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-02-26
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-02-26
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-02-26
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-02-26
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-02-26 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-02-26
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-02-26 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-02-26 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-02-26
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-02-26
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-02-26
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-02-26
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-02-26
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-02-26 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-02-27 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-02-27
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-02-28 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-02-28
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-01 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-01
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-02 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-02
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-03 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-03
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-04 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-04

## R26 Mock 0
Section | Step | Mock/Prod/Both | Task | Sub Task | Details | Status | Resource Type | Assigned Resource/ Confirmer | Planned Duration (mins) | Planned Start Date | Plannned Start Time | Actual Start Time | Actual Stop Time
1 |  | Pre - CALM System Outage | [7 empty] | 2022-03-17
1.1 |  |  | Logistics planning
#REF! | #REF! | Both | Resource plan identified and documented Duke and Vendor engagement | Based on checklist activities, should include: - Resource type - Resource name - Contact information - Applicable backup contacts - Remedy support group info (as necessary) - Escalation paths - Allocation timeline |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-03-10
#REF! | #REF! | Prod | Identify any planned outages for other systems that may impact the release | Check CIRB (change impact review board) outage plans and other IT outages | Known changes: None known | Not Started | Delivery Lead / Manager/ Environment Lead | Derek Freeze / Ginger Altherr |  | 2022-03-10
#REF! |  |  | CRQs / Workorders / Approvals
#REF! | 1 | Prod | Creation of outage CRQ w/appropriate approvals: | Prod CRQ# : ?? |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! | 2 | Both | Assessment of DB Backups necessary, and documentation of appropriate DB backup workorders w/approvals | Activities: NA - Server Backup - Prod ?? – DB Backup - Prod - DB Backup ?? – Mock1 - DB Backup ?? – Mock2 - DB Backup ?? – Mock3 QA | Start of outage backup, pre-data backup | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! | 3 | Both | Creation of any other release specific CRQs/workorders/Incidents w/approvals |  | DBA scripts, Informatica requests, server snapshot requests, etc… | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-10
#REF! |  |  | Code and Architecture Readiness
#REF! | 1 | Both | Confirm Release specific component list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead and Build Manager |  | Not Started | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! | 2 | Both | Confirm Release specific Manual Configuration list is documented/reviewed/approved by Delivery Leads | Provide approved Manual Configuration list to Deployment Lead |  | Not Started | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! | 3 | Both | Confirm all data feeds are stored on SharePoint and are current | Data Feeds: R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment, Development, Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! | 4 | Prod | Implement Updated Remedy Incident Lookup spreadsheet on Netcool Console for any new or modified data feeds as part of deployment (This will ensure that Remedy incident tickets will trigger to app support upon failures of these feeds) |  | Netcool Files | Not Started | Delivery Lead / App Support | Derek Freeze / Shawn Linnen |  | 2022-03-10
#REF! | 5 | Both | Build package with approved component list in designated source environment. | Included components should be peer reviewed | Same package as previously deployed | Not Started | Build Manager | Naresh Methuku |  | 2022-03-10
#REF! | 6 | Both | Peer review of components included in package build. |  |  | Not Started | Lead Developer | Chase Farley |  | 2022-03-10
#REF! | 7 | Both | Generate package (successfully), and store in Subversion (SVN) | Confirm that package name is updated to match environment and date to prevent confusion when pulling from SVN. | Will use same package from Mock 1 | Not Started | Build Manager | Naresh Methuku |  | 2022-03-10
#REF! | 8 | Both | Provide SVN location to Deployment Lead and Development team. | SVN for Prod R25: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR25/Go-Live/ | Package Name: CALMPACKAGE_R25_Components_Feature_Complete_10202021 | Not Started | Build Manager | Naresh Methuku |  | 2022-03-10
#REF! | 9 | Both | Confirm if any new AD Groups or roles are included in release, and that they have been appropriately setup. QA and PROD connect to NAM All other non-prods connect to NAMDEV | New AD Groups: | None for R26 | NA | Lead Developer / Delivery Lead | Chase Farley / Derek Freeze |  | 2022-03-10
#REF! |  |  | End User Readiness
#REF! | 1 | Prod | Send out Release Awareness communications at least 1 week prior to deployment |  | R25 Communications - All Documents (duke-energy.com) | NA | Change Management | Steve Joslin |  | 2022-03-10
#REF! | 2 | Prod | At least 7 days prior to deployment: Confirm any CALM task due-dates are not impacted by deployment outage window by running the following reports with search criteria for the outage start date to several days after deployment window ends: Task Magement Application: - ACR Due Dates Report - Due Tasks All | Pay specific attention to Patch Source Evaluations and Asset Change Requests, but review others also. Check every day for week prior to deployment. (Start Mon AM) |  | NA | App / Business Support | Steve Joslin |  | 2022-03-10
#REF! | 3 | Prod | Communicate to CALM users with due-tasks that may be impacted by the deployment outage window: | Deployment lead should work with Product owner to reach out to these users to ensure time to act on their tasks | R25 Communications - All Documents (duke-energy.com) | NA | Deployment Lead | Steve Joslin |  | 2022-03-10
#REF! | 4 | Prod | Schedule Functional Checkout session(s) with CALM end users |  |  | NA | Deployment Lead / Functional Checkout Lead | Steve / Erin |  | 2022-03-10
#REF! |  |  | Data Readiness
#REF! | 1 | Both | Validate all R26 Data Import templates are stored on SharePoint and ready for deployment activities (4 total templates) | 1_Vulnerability Assessment.Due Date Calcs_R26 2_Network Discovery.Due Date Calcs_R26 3_Wireless Discovery.Due Calcs_R26 4_Team.VAR_R26 |  | Not Started | Deployment Lead / Business Analysts | Erin Manchuso / Derek Freeze |  | 2022-03-17
#REF! |  |  | Data Feed Readiness
#REF! | 1 | Both | Validate all R26 Data feeds are stored on SharePoint and ready for deployment activities | R26 list: -Patch Automation – (1) FoxGuard Scorecard Updates -Vulnerability Assessments – Create VAR -Vulnerability Assessments – Create Network Discovery -Vulnerability Assessments – Create Wireless Review | Migrating as part of R26 package migration | NA | Deployment Lead / Business Analysts | Chase Farley / Derek Freeze |  | 2022-03-17
#REF! |  |  | Day of Outage - Final Prep
#REF! | 1 | Prod | Send out Outage reminder communication to CALM tool users | R26 Communications - All Documents (duke-energy.com) |  | NA | Change Management | Steve Joslin |  | 2022-03-17 | 8:30
#REF! | 2 | Prod | Day-of-outage confirmation that all data feeds have successfully executed prior to taking outage | Check all active data feeds to ensure successful completion. | In case of issues, troubleshoot and ensure successful execution of daily feeds prior to outage being taken | NA | Application Support | Shawn Linnen |  | 2022-03-17
#REF! | 3 | Prod | Confirmation that there are no urgent outstanding CALM production issues | This is a confirmation with App and Business Support. |  | NA | Application Support | Shawn Linnen |  | 2022-03-17
#REF! | 4 | Prod | Final day-of-outage confirmation that impacted due-tasks are addressed before the outage window starts | Run reports in Task Magement Application on day of deployment: Due Tasks All | If tasks aren't complete, communicate impacts to Delivery manager and decision as necessary. | NA | Application Support | Steve Joslin |  | 2022-03-17
#REF! | 5 | Both | Ensure we have day-of-outage web/app server snapshots prior to new CALM package migration | These are scheduled to run nightly, so we should validate that the snap shot was taken prior to the start of the package promotion. | We should plan this to run on-demand during deployment (ticket to server team needed) in the event we have server config changes associated with the release | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
#REF! | 6 | Both | Request on-demand backups if needed | **If current snapshots do not exist ** Request an on-demand backup of server snapshots be taken for our environment | We retain these in the event a rollback is necessary. | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
2 |  | CALM System Outage - Install/Config Activities
2.1 |  |  | Pre-Job Brief
2.1 | 1 | Both | Role Call - Confirmation of needed resources | Reference deployment resource plan and timeline - Shawn, Naresh, Ginger, Chase, Erin | CALM Deployment Contacts | Not Started | Deployment Lead | Steve Joslin | 5 | 2022-03-17 | 17:30
2.1 | 2 | Both | Perform pre-job brief to confirm activities and environment | - Confirm environment for deployment - Confirm High-level outage plan (general outage activities and timeline) | Mock 1 - TEST2 Mock 2 - PFT1 Mock 3 - QA1 Environment Go-live: PROD | Not Started | Deployment Lead | Steve Joslin | 5 | 2022-03-17 | 17:35
2.1 | 3 | Prod | Check for any active service disruptions that might impact the CALM deployment |  | Confirm with Delivery Manager and Environment Lead | NA | Deployment Lead | Derek Freeze | 5 | 2022-03-17 | 17:40
2.1 | 4 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-17
2.1 | 5 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn | 1 | 2022-03-17
2.1 | 6 | Prod | Update CRQ to indicate that work has started (when it's the scheduled start of CRQ outage) |  |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-17 | 18:00
2.2 |  |  | Take Prod System offline to end users
2.2 | 1 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 1 | 2022-03-17 | 18:00
2.2 | 2 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx |  | NA | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-17
2.2 | 3 | Both | Inactivate Patch Automation Data Feeds | Inactivate the following 2 feeds: - Patch Automation - (1) FoxGuard Scorecard Update - Patch Automation - Create Assessments New with R25 (for next time) - PSP: Create CALM Revision History |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-03-17 | 8:47
2.2 | 4 | Prod | Update Archer to Archer Feeds | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support, Lead Developer, Delivery Lead | Shawn Linnen / Derek Freeze / Chase Farley | 8 | 2022-03-17 | 18:05
2.3 |  |  | Database Backups and Server Prep
2.3 | 1 | Both | Request DBA to start database backup | Communicate to assigned DBA that CALM database backup can be taken. | This should be stored in the event a rollback is necessary. | Not Started | Environment Lead | Ginger Altherr | 1 | 2022-03-17 | 18:13
2.3 | 2 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | This DBA driven step can run in parallel with other steps below, but is a pre-req to starting package migration. | Not Started | Environment Lead | Ginger Altherr, Peg Parrott | 30 | 2022-03-17
2.3 | 3 | QA | QA Environment Only: | Confirm Mail Server Shutdown in QA so that prod users do not receive notifications from the environment |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-17
2.3 | 4 | QA | QA Environment Only: | Change port on mail settings in archer control panel (Only environment team can do this) |  | NA | Environment Lead | Ginger Altherr |  | 2022-03-17
2.3 | 5 | Both | Take backup of current images in target env and Copy Image folders from source environment to target | Rename current to "company_files_1" as a backup | Folder: company_files (shared files) - this is shared among all vms - D:\inetpub\wwwroot\RSAarcher\company_files | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-17
2.3 | 6 | Both | Copy images from source environment to target environment | Comes from the TEST2 environment |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
2.3 | 7 | Both | Validate Images Display via spot checks of our landing pages | Log into CALM and navigate around to application landing pages (or all legacy and new applications) and ensure we don't see any missing images |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17
2.4 |  |  | Data Exports (can be performed while db backup is occurring) | BES CSI LINK: | CALM R25 - All Documents (duke-energy.com)
2.4 | 1 | Both | None for R26 |  |  | NA | Application Support | Shawn Linnen / Erin M | 6 | 2022-03-17 | 18:43
#REF! |  |  | Environment Reboot Prior to Install
#REF! | 1 | Prod | Put Prod servers into maintenance mode | Avoid generating High remedy ticket |  | NA | Environment Lead | Ginger Altherr | 3 | 2022-03-17 | 19:00
#REF! | 2 | Both | Bounce all services | Should be performed on ALL app and web servers | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-17
#REF! | 3 | Both | Perform IIS reset | Best practice to sync environment for package promotion readiness | Executed on all app and web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-17
#REF! | 4 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
#REF! | 4 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17
#REF! | 5 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17
#REF! |  |  | LDAP Query Updates
#REF! | 1 | Both | Re-confirm that new AD groups exist prior to amending LDAP queries and migrating code None for R26 | IF this is not done, we cannot migrate code without breaking access rules in CALM (Groups/Roles/Rules will be dropped) | http://ds.duke-energy.com/ADSecuritySearch/ADSearch.aspx | NA | Environment Team / Delivery Lead | Ginger Altherr / Derek Freeze |  | 2022-03-17
#REF! |  |  | ** Decision for Package Migration **
#REF! | 1 | Both | Confirm all dependent activities have been completed and communicate if package migration can begin ** | Confirmation that all items above this are complete with no outstanding defects | All pre-migration steps complete | Not Started | Delivery Lead | Derek Freeze / Chase Farley | 1 | 2022-03-17 | 19:12
#REF! |  |  | Package Migration and Install
#REF! | 1 | Both | Export package from SVN local folder | SVN for Prod R25: https://subversion.duke-energy.com/svn/Security_HR_IT_Solutions/Asset_Change_Workflow/branches/CALMR25/Go-Live/ | Package Name: CALMPACKAGE_R25_Components_Feature_Complete_10202021 | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17 | 19:12
#REF! | 2 | Both |  | Login to Target Environment and import package (from Local SVN Folder) |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 3 | Both | Perform mappings and take screenshots of mappings once completed (If items do not map do not need to take screenshots) See link in comments | Perform mappings Document mappings during lower environment migrations for reference at go-live | Advanced Package Mapping from the Administration dashboard. Go through all mappings with peer reviews. | Not Started | Application Support | Shawn Linnen / Chase Farley | 20 | 2022-03-17 | 19:14
#REF! | 4 | Both |  | Select Execute Mappings |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 5 | Both | Install Package downloaded from SVN folder |  |  | Not Started |  |  |  | 2022-03-17
#REF! | 6 | Both |  | Locate the package under available packages | Ensure name matches the one pulled from SVN | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 7 | Both |  | Click "Install Package" |  | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 8 | Both | Validate Pre-install configurations are selected before installing | 1. Deactivate Target fields and prefix with ZZZ 2. Select all components to install 3. Select the "Create New and Update" option in Archer 4. Select "Override Layouts" option in Archer |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-17
#REF! | 9 | Both | Click Install and wait for installation to complete | Click Install Package and wait for install to complete |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 35 | 2022-03-17 | 19:38
#REF! | 10 | Both | Validate Install completes successfully | Validate package install is successful | Installation returns - "Package partially successful" | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! |  |  | Package Install Validations
#REF! | 1 | Both | Export and review install warnings | Export anomalies to excel sheet and store locally |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 2 | 2022-03-17 | 20:13
#REF! | 2 | Both |  | Send new anomalies excel sheet to Dev team for validation | List Applications impacted by new scope | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 3 | Both |  | Review all anomalies across all applications to ensure no issues with install |  | Not Started | Lead Developer | Chase Farley | 5 | 2022-03-17
#REF! | 4 | Both |  | Take resolution steps for any warnings as necessary | Determine resolution paths and if re-package or re-migration is needed for anything | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
#REF! | 5 | Both |  | Validations with warnings sent to Build Manager |  | Not Started | Lead Developer | Chase Farley |  | 2022-03-17
#REF! | 6 | Both |  | Validation of warnings received and saved in local SVN folder | Can run in parallel Confirm advanced workflow activation list | Not Started | Environment Lead | Sri Katta / Naresh Methuku |  | 2022-03-17
#REF! | 7 | Both | Confirm notifications won't be sent out | Notification reports --> "Notifications Sent" | Pull report and look for the last 24 hours. Look for any notifications since package install. Do as soon as package upload completes into target environment | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-17
#REF! | 8 | Prod | Confirm Archer to Archer data feeds are completing | Applicable when deployment/outage occurs over scheduled data feed timings. | Depends on whether the outage overlaps with scheduled Archer-to-Archer feed timings | NA | Application Support | Shawn Linnen |  | 2022-03-17
#REF! | 9 | Both | Export xml of Global Values List in order to ensure no test or duplicate "OS/Firmware Details" values are migrated to the target enviroment | Application Builder --> Global Values List --> OS/Firmware Details | Export xml file to use for cleanup (Can compare against during validations post-cleanup) | Not Started | Application Support | Shawn Linnen / Chase Farley | 1 | 2022-03-17
#REF! | 10 | Both | Open xml export in Notepad ++ to prep import for bulk delete of (1), CALM, TEST values in Operating System or Firmware | 1. Open xml in Notepad ++. 2.. Search for and Mark the following 4 values: (1), TEST, CALM, NEW 4. Mark value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" in Operating System or Firmware Type 5. Mark First 2 rows of xml file, as well as last row. 6. Remove all unmarked rows 7. Save xml file, as these remaining "marked" rows are the ones to be deleted from CALM 8. Send file to the sysadmin resource that will need it for deployment. | Peer Check values in PROD (NEW and Pending) QA ONLY Make sure we do a basic search and look at TEST or CALM values to be marked. For example, in Asset Code "Whitestown" will show. This should NOT be marked. For Operating System or Firmware type Find value "SAGE-2400-C3414-500-001G1 SAGE-2400-C3414-500-001G1" to be deleted in CALM | Not Started | Application Support | Chase Farley |  | 2022-03-17
#REF! | 11 | Both | Smoke Test Functionality
|  |  | Vulnerability Assessment Reporting (VAR) - Ability to track ports scans, vulnerability scans, wireless scans, and networking discovery tasks in CALM - Creation of VAR Dashboard & reports - Notifications of upcoming VAR deadlines |  |  | Not Started | Application Support | Shawn Linnen / Chase Farley | 18 |  | 20:23
Chase will add these
2.1 |  |  | Manual Configuration Updates
2.1 | 1 | Both | Activate advanced workflows | Listing could change depending on Release - List will come from package install warnings. Cyber Assets will not require activation. | R26: Physical Security Non-Cyber Asset Change Request Asset Change Request Compliance Activities Compliance Sub-Activities (3 levels) Technology Profiles Patch Mitigation Plan Vulnerability Assessment | Not Started | Application Support | Shawn Linnen / Chase Farley | 5 | 2022-03-17 | 20:41 |  |  | Stay | Can Go/Stay
2.1 | 2 | Both | Activate Calculation Schedules | Activate Scheduled calculations | R26: Activate Calculation Schedules: - Asset Reconciliation Recalculation - BES Assets Recalculation - Configuration Reports Recalculation - Cyber Assets records with associated Configuration Reports - Patch Source Evaluations: Aggragation Records - Compliance Activities Reactivation - Compliance Sub Activities Recalculation (3 levels) | Not Started | Application Support | Shawn Linnen / Chase Farley | 6 | 2022-03-17 |  |  |  | Stay | Can Go/Stay
|  | Prod | Activate scheduled report distributions | Asset Integration - EAP Electronic Security Data Asset Integration - Electronic Security Subnet Data Asset Integration - IT SharePoint Extract Asset Integration - IT Tracking ID Extract OT SOC - Cyber Asset Data Extract OT SOC - Vulnerability IP360 Data Extract |  | Not Started | Application Support | Shawn Linnen / Chase Farley
2.1 | 3 | Both | Perform Inventory of Manual Configuration steps | Make manual config changes to the target environment post validation of all warnings and errors. | R25 - Component List and Manual Configurations | Not Started | Application Support | Shawn Linnen / Chase Farley | 45 | 2022-03-17 | 20:52 |  |  | 220 | 3.6667
2.1 | 4 | Both | Peer check confirmation of Manual Configs (occurs real-time during config changes) | Validate all manual config changes to the target environment |  | Not Started | Lead Developer | Chase Farley |  | 2022-03-17
2.1 | 5 | Prod | Confirm all new or modified data feeds have job-status e-mail notifications configured in PROD |  | netcoolcorpp@duke-energy.com | NA | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
2.1 | 6 | Prod | Modify CALM Homepage Announcement for Release specific Information | Determine if necessary on a release by release basis. - Show All - Admin Dashboard- - Announcements - | Release 26 features are now available! Key Updates: • Vulnerability Assessment Reporting enhancements | NA | Application Support / Delivery Lead | Shawn Linnen / Derek Freeze | 3 | 2022-03-17 | 21:37
2.1 | 7 | Both | Perform import to cleanup OS/Firmware Details duplicate values in Global Values Lists | Bulk delete duplicates with delete import template (Manually delete instead of manageable) | Application Builder --> Global Values List --> OS/Firmware Details --> Bulk delete --> upload OS/Firmware Details Delete template | Not Started | Application Support | Shawn Linnen / Chase Farley | 10 | 2022-03-17
2.1 | 8 | Both | OS/Firmware Details checkout | Perform checkout and manually delete any other values (#N/A, tiered values with colons, etc… (1) - (20) Search | 1. Perform same export of OS/Firmware Details Values and validate a search does not find following 4 values: (1), TEST, CALM, NEW | Not Started | Application Support | Shawn Linnen / Chase Farley |  | 2022-03-17
2.1 | 9 | Both | Export Asset Codes Global values list to ensure no duplicate asset codes exist. Specifically look out for the ones documented, but review entire export for others. If Duplicates exist, review and manually clean up. | Application Builder --> Global Values List --> Asset Codes --> Export Open the xml export in Notepad ++ and review for duplicate "(1)" values to notate for manual deletion Manually delete those duplicate values | 0514 - Powerline(1) 0547 - Wire Road(1) DEBA - Debary Solar Common(1) FSO2 - FSO Backup(1) HECC - Harrison ECC(1) LC17 - Lincoln CT Unit 17(1) MC01 - Maiden Creek Solar Unit 1(1) RHLS - Holstein Solar, LLC(1) RLPS - Lapetus Energy Project, LLC(1) RMES - Mesteño Windpower, LLC(1) RNRS - North Rosamond Solar, LLC(1) RRMS - RE Rambler, LLC(1) SF00 - Santa Fe(1) | Not Started | System Administrator | Shawn Linnen / Chase Farley | 5 | 2022-03-17 | 12:22
2.11 |  |  | Data Export for Import Template Validations
2.11 | 1 | Both | None for R26 |  | Post-install export | NA | System Administrator | Shawn Linnen / Erin M | 3 | 2022-03-17
#REF! |  |  | ** Completion of Code Install/Configs ** - DB Backup point
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. | Not Started | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-17 | 21:45
3 |  | CALM System Outage - Data Import Activities
3.1 |  | Both | 1_Vulnerability Assessment.Due Date Calcs_R26
3.1 | #REF! | Both | Upload import template: "1_Vulnerability Assessment.Due Date Calcs_R26" a. Upload – Update Existing Records i. Cyber Asset Identifier, Business Area, Responsible Team, Last Active VA Completion Date, Last VA Completion Date | Steps: 1.Save template locally 2. Navigate to Vulnerability Assessment application 3. Navigate to Data Import 4. Import file “1_Vulnerability Assessment.Due Date Calcs_R26” 5. Update Existing Records (Cyber Asset Identifier) 6. Validate import field mapping (everything should automap 1:1 7. Import 8. Validate successful import |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 3 | 2022-03-18
3.1 | #REF! | Both | Technical checkout of import template | 1. Build and export report from Vulnerability Assessment with the following fields: Fields: Vulnerability Assessment - Cyber Asset Identifier - Business Area - Responsible Team - Last Active VA Completion Date - Last VA Completion Date Filter: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comment |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-18
#REF! |  | Both | 2_Network Discovery.Due Date Calcs_R26
#REF! | 1 | Both | Upload import template: "2_Network Discovery.Due Date Calcs_R26" a. Upload - Update Existing Records i. Electronic Security Name, Business Area; Associated Team;Legacy Completion Date | Steps: 1.Save template locally 2. Navigate to Network Discovery Assessment application 3. Navigate to Data Import 4. Import file 2_Network Discovery.Due Date Calcs_R26" 5. Create Update Existing Records 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2022-03-18 | 22:08
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Network Discovery Assessment with the following fields: - Electronic Security Name - Business Area - Associated Team - Legacy Completion Date Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2022-03-18
#REF! |  | Both | 3_Wireless Discovery.Due Calcs_R26
#REF! | 1 | Both | Upload import template: "3_Wireless Discovery.Due Calcs_R26" 3_Wireless Discovery.Due Calcs_R26 b. Upload - Update Existing Records i. Physical Security Name; Business Area; Associated Team; Legacy Completion Date | Steps: 1.Save template locally 2. Navigate to Wireless Discovery Assessment application 3. Navigate to Data Import 4. Import file "3_Wireless Discovery.Due Calcs_R26 6. Validate import field mapping (should be automapped and map 1:1) 7. Import 8. Validate successful import |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26 | 22:15
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Wireless Discovery Assessment with the following fields: - Physical Security Name - Business Area - Associated Team - Legacy Completion Date Use the following filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26
#REF! |  | Both | 4_Team.VAR_R26
#REF! | 1 | Both | Upload import template: "4_Team.VAR_R26" a. Upload – Create New Records i. Team Name, Business Area, Team Lead, Team Reviewer, Team Members | Steps: 1.Save template locally 2. Navigate to Team Application 3. Navigate to Data Import 4. Import file "4_Team.VAR_R26" 5. Create New Records 6. Validate import field mapping (should be automapped and map 1:1) - Don't map Tracking Id (Patch Mitigation Plan) 7. Import 8. Validate successful import |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 10 | 2021-10-26
#REF! | 2 | Both | Technical checkout of import template | 1. Build and export report from Team Application with the following fields: - Team Name - Business Area - Team Lead - Team Members - Team Reviewer Filter criteria: - None 2. Use comparison macro to confirm report with original import template (Confirm every field is populated correctly and record count matches) 3. Store verification evidence on SharePoint (link in comments) |  | Not Started | Application Support | Shawn Linnen / Erin - Nitisha / Chase Farley | 5 | 2021-10-26
4.17 |  |  | Reactivate Patch Automation Feeds
4.17 | 1 | Both | Activate PSE Data feeds | Activate PSE Data feeds Patch Automation - (1) FoxGuard Scorecard Update Patch Automation - Patch Assessment Create New with R25 (for next time) - PSP: Create CALM Revision History |  | Not Started | System Administrator | Shawn Linnen / Chase Farley | 3 | 2021-04-09 | 23:05
#REF! |  |  | ** Perform DB Backup **
#REF! | 1 | Both | DBA Takes Backup - Confirm completion of database backup and document timings | Confirm start time of the backup and provide to deployment lead. Confirm completion time also. | Must capture timestamp of backup so Ginger can use it for environment refresh later. (Per Wilson) | Not Started | Environment Lead | DBA Assigned to Workorder | 30 | 2022-03-18 | 23:08
** Target Stopping point for Thursday Night **
#REF! |  |  | Health Check
#REF! | 1 | Both | Execute Full suite of Release 26 Health Check Routines (This can be performed in parallel while other imports/activities progress) - by anyone else with sysadmin | CALM R25 Health Checks |  | Not Started | System Administrator / Delivery Lead | Shawn Linnen / Shruthi Kuna / Naresh Methuku / Derek Freeze | 30 | 2022-03-18 | 8:30
#REF! |  |  | Confirm readiness for prod return and functional checkout (Plan for 1 hour to prep env for functional checkout)
#REF! | 1 | Both | Confirm that no issues from CALM System Health Checks before functional checkout |  |  | Not Started | Deployment Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-18 | 9:00
#REF! | 2 | Both | Confirmation that all steps to deploy Release updates (package, manual configs, and data activities) are completed and we are ready to proceed |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley | 1 | 2022-03-18
#REF! |  |  | Prod-return prep
#REF! | 1 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | NA | Environment Lead | Ginger Altherr | 2 | 2022-03-18
#REF! | 2 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 2 | 2022-03-18 | 9:05
#REF! | 3 | Both | Bounce all services DO not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-18
#REF! | 4 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-18
#REF! | 5 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
#REF! | 5 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-18
#REF! | 6 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-18
#REF! |  |  | Re-enable any integrations/feeds that were placed on hold
#REF! | 1 | Prod | NA for R26 |  |  | NA | Application Support | Shawn Linnen |  | 2022-03-18
3.1 |  |  | PROD Return For Functional Checkout
3.1 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on (web and app servers? Just web servers? Etc...) | NA | Environment Lead | Ginger Altherr | 5 | 2022-03-18 | 12:45
3.1 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | NA | Application Support | Shawn Linnen | 1 | 2022-03-18
4 |  | R26 Functional Checkout
4.1 |  |  | Functional Checkout
4.1 | 1 | Both | Communicate to functional checkout resources that checkout can begin Ensuring functional checkout scheduling (pre-outage) | Functional Checkout will be after the system is back online |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-18 | 13:00
4.1 | 2 | Both | Functional Checkout Session (Scope Table link) | Transmission | Transmission- Michael Swift | Not Started | End users | Michael Swift | 60 | 2022-03-18 | 13:00
4.1 | 3 | Both |  | IT | IT- William Baucom | Not Started | End users | William Baucom |  | 2022-03-18
4.1 | 4 | Both |  | EPS | EPS – Cory Burns | Not Started | End users | Cory Burns |  | 2022-03-18
4.1 | 4 | Both |  | BSG | BSG – Shruthi Kuna | Not Started | End users | Shruthi Kuna |  | 2022-03-18
4.2 |  |  | Functional Checkout Success Confirmation
4.2 | 1 | Both | * Confirmation of Successful functional checkout * |  |  | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-18 | 14:00
4.3 |  |  | Take Prod System offline to end users
4.3 | 1 | Prod | Communicate instructions to Deployment Team for accessing the environment for deployment while the Splash Page is displayed | Environment team to provide direct server url (Ginger/Sri) |  | NA | Environment Lead | Ginger Altherr / Sri Katta | 1 | 2022-03-18 | 14:00
4.3 | 2 | Prod | Confirm direct server access prior to taking primary URL offline. |  |  | NA | Environment Lead / App Support | Ginger Altherr / Shawn Linnen | 1 | 2022-03-18
4.3 | 3 | Prod | Portal re-direct to splash page: - Performed by renaming healthcheck files | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on Web Server 1 | NA | Environment Lead | Ginger Altherr | 5 | 2022-03-18
4.3 | 4 | Prod | Validation of CALM site access re-direct to splash page by accessing via the link on the CALM portal. (Expected result is that the Site Maintence Splash page displays) | NERC CIP CALM Portal link |  | NA | Delivery Lead | Derek Freeze | 1 | 2022-03-18
4.3 | 5 | Prod | Confirmation that Archer to Archer Feeds are still pointed to web server url | From the data feed settings in the application, the following feeds need to be updated to run every day of the outage via this method 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. Recurrence - Compliance Activities and Sub-Activities 26. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 27. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 28. Trigger Based Tasks - Impact Rating Mismatch 29. Trigger Based Tasks - PSP Ready to be Commissioned | Enables feeds to successfully run during Deployment System Outage. feeds should reference the server URL instead of the VIP URL (which will fail during the outage due to our splash page healthcheck): CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) | NA | Application Support | Shawn Linnen | 1 | 2022-03-18
4.4 |  |  | Saturday AM - Health Checks
4.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-19 | 9:00
4.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-19
4.5 |  |  | Prod-return prep
4.5 | 1 | Prod | ** Confirm successful health checks and Readiness for Production system being returned to end users for go-live | Health Checks should have been successful with no issues outstanding that will have significant impact to end users |  | Not Started | Delivery Lead | Derek Freeze | 1 | 2022-03-19 | 10:00
4.5 | 2 | Prod | Not applicable for QA: Confirm Notification engine ON and configured appropriately to send emails | Validate e-mail notification settings | DO NOT perform in QA | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-19
4.5 | 3 | Both | Confirm whether any data feeds are currently executing |  |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.5 | 4 | Both | Bounce all services Do Not perform while datafeeds running |  | Best practice to sync environment for package promotion readiness - If service says "automatically", it should be restarted - If it's disabled, they should be left alone -- RSA Archer Configuration (automatic) -- RSA Archer Job Engine (automatic) -- RSA Archer Workflow (automatic) -- RSA Archer Queuing (automatic) -- RSA Archer Job Engine (automatic) | Not Started | Environment Lead | Ginger Altherr | 10 | 2022-03-19
4.5 | 5 | Both | Perform IIS reset Do Not perform while datafeeds running | Best practice to sync environment for package promotion readiness) | Executed on all web servers | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
4.5 | 6 | Both | Dequeue and requeue the archer jobs/services. | This will help with general maintenance for the impacts our clean up jobs have had on data feeds |  | Not Started | Environment Lead | Ginger Altherr |  | 2022-03-19
4.5 | 6 | Both | Confirm access to target environment after Services and IIS restarted | Via direct server url (splash page should still be displayed for end users) |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.5 | 7 | Both | Click on the workflow job troubleshooter to ensure that the workflow is working | Validate workflow running |  | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.5 | 8 | PROD | Take PROD servers out of maintenance mode |  |  | Not Started | Environment Support | Ginger Altherr / Sri Katta | 5 | 2022-03-19
4.6 |  |  | Prod Return
4.6 | 1 | Prod | Remove portal redirect | Rename Health Check file on each server | Need confirmation of all servers this is necessary to be performed on | Not Started | Environment Lead | Ginger Altherr | 2 | 2022-03-19 | 10:21
4.6 | 2 | Prod | Validation of CALM site access | https://dukeenergy.sharepoint.com/sites/portal/our-company/NERC-CIP/Pages/CALM-Tool.aspx | Can be done by anyone with CALM Prod access | Not Started | Application Support | Shawn Linnen | 1 | 2022-03-19
4.7 |  |  | Archer to Archer Feed updates
4.7 | 1 | Prod | Step NOT needed if A2A feeds are already pointed to VIP Revert Archer to Archer data feed changes to use the VIP (https://calm.duke-energy.com/RSAarcher/ ) instead of the Server URL | From the data feed settings in the application, the following feeds need to be switched back to the vip url so that they continue to successfully run every day once the outage is complete. 1. Asset Reconciliation - Create CALM ARs 2. Asset Tagging - Create ATRs 3. Asset Tagging - Map Cyber Assets 4. Asset Tagging - Trigger Notifications 5. Asset Tagging - Update Cyber Assets 6. Configuration Integration - (3a) Justified Ports Update Subform Clear Contents 7. Configuration Integration - (3b) Justified Ports Update Subform Cyber Assets 8. Configuration Integration - (3c) Justified Ports Flag Records 9. Data Automation - (2)Cyber Assets Data Mapping 10. Data Automation - (3)Cyber Assets Data Mapping (Excluding Non-Classified Except LEAC) 11. Data Automation - (4) Cyber Assets Data Mapping (Only Non-Classified) 12. Manual Baselines - (1)Set to Processing 13. Manual Baselines - (2)Create Elements (OS/FW and Patches) 14. Manual Baselines - (3)Create Elements (Software and Justified Ports) 15. Manual Baselines - (4)Remove Elements 16. Manual Baselines - (5)Create Baseline Elements from Device Type (OS/Firmware and Patches) 17. Manual Baselines - (6)Create Baseline Elements from Device Type (Software and Justified Ports) 18. Manual Baselines - (7)Create Baseline History 19. Manual Baselines - (8)Set to Processed 20. Patch Automation - (2) Create FoxGuard 21. Patch Automation - (3) Create Manual 22. Patch Automation - (5) Update Records Approaching Due Date 23. Patch Automation - (6) New Manual Technology Profiles to In-Flight Patch Source Evaluations 24. Patch Automation - Create Assessments 25. PSP: Create CALM Revision History 26. Recurrence - Compliance Activities and Sub-Activities 27. Trigger Based Tasks - BES CS, BES Assets Impact Rating Mismatch 28. Trigger Based Tasks - Compliance Hierarchy Role Change Evaluation 29. Trigger Based Tasks - Impact Rating Mismatch 30. Trigger Based Tasks - PSP Ready to be Commissioned 31. Vulnerability Assessments - Create Network Discovery 32. Vulnerability Assessments - Create VAR 33. Vulnerability Assessments - Create Wireless Review | Enables feeds to successfully run while system is back online. Feeds should reference the VIP URL rather than the server URL CALM PROD VIP: https://calm.duke-energy.com/RSAarcher/ Win2016 Prod Web Server 1: https://WCNCCRPCALMWSP1.nam.ent.duke-energy.com/RSAarcher/ Review to ensure this is the full list Game-time decision based on outage window during deployment. Check feed schedules and confirm when changes need to be applied if still in outage. (set reminder to address by given time) https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Environment%20Team%20-%20Build%20and%20Deploy%20Folder/Prod%20Copy%20Down%20Data%20Feeds.xlsx | Not Started | Application Support / Delivery Lead / Lead Developer | Shawn Linnen / Derek Freeze / Chase Farley | 10 | 2022-03-19 | 10:24
4.8 |  |  | Outage complete confirmation
4.8 | 1 | Prod | Confirm all Code deployment activities have been successfully completed for Monday |  |  | Not Started | Deployment Lead | Derek Freeze | 2 | 2022-03-19 | 10:34
4.8 | 2 | Prod | Decision to complete go-live communication | 1. Communicate Decision to Environment/Deploy team 2. Communicate decision to change resource to prep comm |  | Not Started | Delivery Leads / Manager | Derek Freeze / Ralph Nelson | 1 | 2022-03-19
4.9 |  |  | End User communications and materials
4.9 | 1 | Prod | Go live communications sent out to business areas and stakeholders | (For non-prod, e-mail the entire team distribution to confirm mock complete and readiness for next activities) | Text/Call to confirm Change Mgmt readiness to send this comm text either Adele (917-602-9966) or Lucy (240-481-8721) when deployment wraps up | Not Started | Change Management | Steve Josllin | 2 | 2022-03-19
4.9 | 2 | Prod | Confirm CALM Portal Updates are made | Portal Updates post deployment with Job Aids - Confirm was posted successfully |  | Not Started | Change Management | Steve Josllin | 1 | 2022-03-19
4.1 |  |  | Post-Code deploy logistics
4.1 | 1 | Prod | Confirm that daily system health checks are scheduled for the week following deployment |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Lead | Derek Freeze | 1 | 2022-03-19
4.1 | 2 | Prod | Update the Ready for Prod defects in ALM |  |  | Not Started | Lead Developer | Chase Farley | 30 | 2022-03-19
5 |  | Release Closeout
5 | 1 | PROD | Communicate to Sponsors and Key Support and Business Stakeholders that Release (Inclusive of entire patch cycle) has been validated and completed. BAU processes will be followed going forward |  |  | Not Started | Deployment Lead | Derek Freeze |  | 2022-03-19 | 11:00
6 |  | Post - CALM Health Checks
6.1 |  |  | Sunday AM - Health Checks
6.1 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-20 | 9:00
6.1 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-20
6.2 |  |  | Monday AM - Health Checks
6.2 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-21 | 9:00
6.2 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-21
6.3 |  |  | Tuesday AM - Health Checks
6.3 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-22 | 9:00
6.3 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-22
6.4 |  |  | Wednesday AM - Health Checks
6.4 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-23 | 9:00
6.4 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-23
6.5 |  |  | Thursday AM - Health Checks
6.5 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-24 | 9:00
6.5 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-24
6.6 |  |  | Friday AM - Health Checks
6.6 | 1 | Prod | Perform CALM System Health Check routine |  | https://team.duke-energy.com/sites/ppma/NERC%20CIP%20Cyber%20Asset%20Lifecycle%20Management/Project%20Documents/Deploy/Releases/Release%2021/R21%20-%20CALM%20Health%20Checks.xlsx | Not Started | Deployment Team (Deployment lead, app supp, bus supp, env support, developers) | Derek Freeze / Chase Farley / Shawn Linnen | 60 | 2022-03-25 | 9:00
6.6 | 2 | Prod | If any issues are found during health check, document (via defect if necessary) and address |  |  | Not Started | Delivery Lead / Lead Developer | Derek Freeze / Chase Farley |  | 2022-03-25

## Resource Plan
Name | Role | Contact #
Derek Freeze | Delivery Lead | 704-490-3585
Ralph Nelson | Delivery Manager | 513-260-4891
Chase Farley | Lead Developer | 678-995-9626
Naresh Methuku | Developer | 323-861-2110
Rajeev Matta | Developer | 270-564-6649
Brandon Owens | Developer | 803-444-4121
Erin Manchuso | Business Analyst | 508-298-9127
Kourtney Conway | Product Owner | 704-806-5396
Casey Lutz | Product Owner | 980-329-0930
TaKayla Sexton | Scrum Master | 828-775-4986
Ricardo Tovar | Test Lead | 512-669-0503
Ginger Altherr | Environment Support | 704-881-1853
Srikanth Katta | Environment Support | 603-733-9766
Ryan Schenk | Application Support | 803-431-5027
Shawn Linnen | Application Support | 704-771-8240
Peg Parrott | SQL DBA Support | Via Ginger
Steve Joslin | Deployment Lead | 803-413-0703